# Executive Change Summary: Operations Analytics & Workforce Intelligence MVP

## Project Scope Alignment

Original Scope: The initial project blueprint encompassed a comprehensive suite of six dashboards: Executive Overview, Operations Performance, Quality Assurance, Workforce Management, Appeals Management, and Financial Performance.

Current MVP: The delivered Minimum Viable Product (MVP) has been strategically narrowed to deliver maximum operational value, featuring Operations Analytics, Workforce Management (WFM), and a newly introduced Workforce Demand Forecasting module.

Deferred Scope: To prioritize analytical depth, the Quality Assurance (QA), Appeals Management, and Finance dashboards have been deferred to subsequent roadmap phases.

## Key Enhancements & Governance

Major Analytical Enhancement: The MVP introduces a native Workforce Demand Forecast, elevating the platform from purely historical reporting to providing actionable, forward-looking predictive analytics for resource planning.

Major Governance Decision: A strict data-validation protocol was enforced throughout implementation. Unsupported or misleading KPIs were expressly not fabricated; instead, they were proactively deferred or fundamentally redesigned based on rigorous data validation to maintain absolute reporting integrity.

## Data-Quality Findings

Extensive data profiling during the execution phase surfaced several critical realities that drove the strategic scope adjustments:

Queue Utilization was deferred due to a lack of reliable total-capacity metrics in the source data.

Planned Absenteeism could not be calculated as a distinct, reliable category within the workforce semantic models.

Cebu Workforce Coverage presented a localized data gap; while employee master data exists, corresponding operational workforce records were absent.

Finance Date-Range anomalies necessitated pausing the financial module to avoid timeline overruns and ensure reporting accuracy.

## Overall Outcome

This strategic realignment resulted in a smaller but analytically stronger, highly credible, and thoroughly defensible MVP. By refusing to compromise on data integrity, the platform provides reliable decision-support tools today while establishing a trustworthy foundation for future operational expansions.

# PROJECT CHANGE LOG & IMPLEMENTATION VARIANCE DOCUMENT

Project: Operations Analytics & Workforce Intelligence Platform

Document Version: V1.0

Document Date: 01 September 2026

Document Status: Final MVP Change Record

# 1. ORIGINAL PROJECT BASELINE

The original project was designed as an Operations Analytics & Workforce Intelligence platform intended to provide centralized operational reporting and decision support.

The original scope envisioned six major dashboards:

Executive Overview

Operations Performance

Quality Assurance

Workforce Management

Appeals Management

Financial Performance

The broader solution vision included:

Centralized operational reporting

Consistent KPI definitions

Cross-functional operational visibility

Workforce analytics

Quality analytics

Appeals analytics

Financial analytics

Drill-through analysis

Interactive Power BI dashboards

Future predictive analytics

Future AI-driven capabilities

Near-real-time / real-time operational visibility as a future-state capability

Original Workforce Management (WFM) Specifications:

KPI cards

Headcount vs Required Headcount

Shrinkage Breakdown

Schedule Adherence Trend

Occupancy by Process

Employee WFM Matrix

Staffing / workforce analysis

Planned vs unplanned shrinkage / absenteeism

Original Financial Dashboard Specifications:

Total Revenue

Total Costs

Labor Cost

Overhead Cost

Gross Margin

Cost per Case

Billed Hours

Revenue Leakage

SLA Penalties

Client profitability / financial performance

Original Operations Dashboard Specifications:

Cases Reviewed

Open Backlog

SLA Compliance

AHT

Productivity

Active Reviewers

Queue Utilization

Escalation Rate

Site / operational performance

# 2. ACTUAL MVP DIRECTION

During implementation, the project scope was intentionally reduced to prioritize analytical depth, data validity, interview relevance, and delivery speed.

The current Minimum Viable Product (MVP) focuses primarily on:

Operations / Executive operational reporting

Workforce Management

Predictive demand analysis within the WFM dashboard

The following scope items were deferred:

Quality Assurance dashboard

Appeals Management dashboard

Finance dashboard

This decision reflects deliberate scope control and requirement management, rather than a failure to complete the original requirements. The strategic objective was to produce fewer dashboards with rigorous analytical depth over a large volume of shallow, unvalidated dashboards.

# 3. CHANGE SUMMARY

| Change ID | Area | Original / Baseline Requirement | Actual Implementation | Reason for Change | Impact | Status |
| --- | --- | --- | --- | --- | --- | --- |
| CHG-001 | Overall Project Scope | Six dashboards planned: Executive, Operations, QA, WFM, Appeals, Finance. | Scope narrowed to prioritize Operations/Executive reporting, WFM, and predictive demand forecasting. | Limited project timeline and strategic decision to prioritize analytical quality and depth over dashboard quantity. | Reduced number of implemented dashboards, but stronger analytical depth in Operations and WFM modules. | Implemented MVP scope / deferred remaining. |
| CHG-002 | Operations Dashboard | Queue Utilization planned as a headline operational KPI. | Queue Utilization was not implemented as a headline KPI. | Available dataset lacked a reliable total queue capacity measure required for accurate calculation. | Queue Utilization removed from the dashboard to avoid fabricating metrics. | Deferred (Data Limitation). |
| CHG-003 | Operations / Site Summary | Process Name considered part of the detailed reporting structure. | Process Name removed from the Site Summary table. | Site Summary was simplified to focus strictly on site-level workforce and operational decision metrics. | Delivered a simpler, more executive-focused summary table. | Implemented. |
| CHG-004 | WFM Data Model | Documentation referenced Fact_Workforce as the workforce fact source. | Implementation uses vw_Workforce_Dashboard as the practical reporting source. | Initial DAX measures referencing Fact_Workforce generated Expression Errors. Corrected to align with actual semantic model connections. | Improved data model alignment and eliminated DAX errors. | Implemented. |
| CHG-005 | WFM DAX | Initial measures generated errors due to incorrect fact table references. | Measures corrected to reference vw_Workforce_Dashboard and organized under WFM Measures. | Need for validated measures covering hours, headcount, absenteeism, and capacity analysis. | Corrected calculations, enabling the WFM dashboard to operate accurately. | Implemented. |
| CHG-006 | WFM Absenteeism / Shrinkage | Requirement anticipated planned vs. unplanned shrinkage/absenteeism analysis. | Uses available absenteeism/shrinkage type information without a 'planned' split. | Dataset does not provide a reliable 'Planned Leave' category. Decision made not to fabricate data. | Planned vs. unplanned absenteeism is not presented as a separate KPI. | Deferred (Data Limitation). |
| CHG-007 | WFM Metrics | Staffing Gap and Absent Employees treated as independent metrics. | Dashboard interpretation reviewed; noted that both produced the same counts in the dataset. | Data validation revealed overlap between the two metrics. | Avoided presenting duplicate information as independent analytical signals. | Validated / Documented Limitation. |
| CHG-008 | WFM KPI Validation | Initial Occupancy/Utilization formulas produced identical percentages across all sites. | Investigated and validated against Logged Hours, Handle Hours, Actual HC, and Required HC. | Data validation confirmed Logged Hours and Handle Hours are distinct. Previous formula was incorrect. | Improved metric credibility and prevented misleading site comparisons. | Implemented (Post-Validation). |
| CHG-009 | WFM Data Quality | Cebu metrics required for complete organizational reporting. | Cebu treated as unavailable/N/A for workforce-capacity analysis. | Cebu has 4 employees in Dim_Employee and operational demand, but zero records in vw_Workforce_Dashboard. | Cebu workforce metrics cannot be reliably calculated; prevents manufacturing capacity data. | Exception Documented. |
| CHG-010 | WFM Dashboard Visual Design | Dedicated Headcount vs Required Headcount visual planned for main canvas. | Visual removed from main canvas and replaced with Workforce Demand Forecast. | Staffing Gap by Site communicates shortages adequately. Forecast adds predictive value. | Reduced visual redundancy; introduced predictive analytics. | Implemented. |
| CHG-011 | WFM Predictive Analytics | AI-driven forecasting considered a future-state capability. | Baseline Workforce Demand Forecast added using Power BI's native time-series forecasting. | To introduce practical predictive analytics while remaining faithful to the available dataset constraints. | Provides historical demand plus forward-looking demand forecasting natively. | Implemented. |
| CHG-012 | Predictive Analytics | Complex AI/ML forecasting model. | Power BI forecasting baseline implemented. | Historical data showed stable demand, weak seasonality, and varied site volatility. | Avoids overstating the capability of the current solution to stakeholders. | Baseline Implemented / Advanced Deferred. |
| CHG-013 | WFM Predictive / Risk Analytics | Capacity Risk % intended as a major headline dashboard visual. | Capacity Risk % calculated but retained only as a supporting calculation. | Logic resulted in ~104% across most sites, reflecting existing staffing ratios rather than differentiated predictive risk. | Maintains analytical integrity and prevents a weak metric from becoming an executive KPI. | Supporting Analysis Retained / Headline Deferred. |
| CHG-014 | Power BI UX | Standard hover tooltips on visuals. | Separate dynamic tooltip page created using WFM-specific measures. | To improve contextual analysis without cluttering the main dashboard canvas. | Improved contextual analysis and user experience. | Implemented. |
| CHG-015 | Finance Dashboard | Comprehensive financial KPIs (Revenue, Total Cost, Margin, Profit, Leakage). | Finance dashboard paused/deferred. | Actual dataset (vw_Finance_Dashboard) lacks reliable cost, margin, penalty, and profit fields. | Avoided creating unsupported/fabricated financial metrics. | Deferred (Data Limitation). |
| CHG-016 | Finance Data / Reporting | Reporting period aligned to January 2021 – August 2026. | Finance implementation paused due to broad date anomalies. | Finance view contains dates ranging from 2000–2050. Date slicer/filtering produced unexpected behaviors. | Time prioritized toward WFM/Operations rather than extensive date-model troubleshooting. | Deferred (Data Limitation). |
| CHG-017 | Quality Assurance | QA dashboard including QA Score, Fatal Error Rate, Audit Coverage. | QA dashboard deferred to a later phase. | Strategic scope reduction to prioritize WFM and Operations analytics. | QA capabilities remain in the future roadmap. | Deferred. |
| CHG-018 | Appeals Management | Appeals dashboard including Overturn Rate, Resolution Time, Appeal Backlog. | Appeals dashboard deferred to a later phase. | Strategic scope reduction to prioritize core operational modules. | Appeals analytics remain in the future roadmap. | Deferred. |
| CHG-019 | Real-Time Visibility | Real-Time / Near-Real-Time End-to-End Operational Visibility. | Demonstrated analytical architecture for future real-time use, but utilizing batch/historical data. | True real-time streaming infrastructure was outside practical MVP scope limits. | Real-time visibility established as a future-state architecture, not a current streaming feature. | Future State. |

# 4. DATA QUALITY & DATA AVAILABILITY FINDINGS

During the requirements gathering and execution phases, rigorous data profiling led to the following definitive findings:

Queue Utilization could not be reliably calculated because a suitable total capacity field was unavailable in the source data.

Planned Leave / Planned Absenteeism was not available as a reliable category within the workforce semantic views.

Staffing Gap and Absent Employees produced overlapping counts in the existing data hierarchy.

Cebu exists in employee master data but has no corresponding WFM records, creating a localized data coverage gap.

Finance data contains a broad and anomalous date range spanning from approximately 2000 to 2050.

Finance views do not contain the cost/profit fields required to fulfill the original Finance BRD specifications.

Enterprise demand is highly stable, exhibiting minimal year-over-year trend.

Weekday demand seasonality is weak across the enterprise dataset.

Site-level demand varies significantly in absolute volume between locations.

Site-level demand volatility differs notably, with smaller operational sites showing higher relative volatility compared to larger sites.

# 5. PREDICTIVE ANALYTICS EVOLUTION

Original Concept:

AI-driven forecasting and predictive analytics were initially envisioned as comprehensive, future-state capabilities bridging operations and workforce management.

Current Implementation:

A practical Power BI native Workforce Demand Forecast was implemented to provide immediate baseline predictive value.

Forecast Input: Cases Handled

Forecast Horizon: 3 months

Confidence Interval: 95%

Current Interpretation: This is a baseline predictive forecast, not a full Artificial Intelligence / Machine Learning (AI/ML) model.

Future Enhancement:

A production-grade ML forecasting model will be developed in future phases. This model could incorporate:

Historical demand

Site geography

Day of week

Seasonality

Workforce availability

Staffing levels

Shrinkage

Productivity

Operational events

Other relevant business drivers

Future model evaluation standards must utilize formalized metrics including:

MAE (Mean Absolute Error)

RMSE (Root Mean Squared Error)

MAPE (Mean Absolute Percentage Error) or another appropriate percentage error metric.

Note: It is explicitly stated that these advanced ML features, models, and error evaluations were NOT implemented in the current MVP.

# 6. REAL-TIME END-TO-END VISIBILITY

Current Architecture:

Power BI currently provides interactive historical and near-current operational visibility based on available batch data refreshes. It does not utilize real-time streaming APIs.

Future Architecture:

The conceptual foundation has been laid for a real-time control tower. The future-state data pipeline will connect:

Operations -> Workforce Management -> Quality -> Finance -> Forecasting -> Risk Detection -> Alerts -> Management Decision

This represents a future-state architectural goal and is not currently implemented as a live streaming environment in the MVP.

# 7. REQUIREMENT-TO-IMPLEMENTATION TRACEABILITY

| Requirement | Original Scope | Implemented? | Change | Reason | Current Status |
| --- | --- | --- | --- | --- | --- |
| Executive Overview | Cross-functional exec summary | Yes | Prioritized | Focus on core reporting | Implemented |
| Operations Dashboard | Comprehensive site Ops metrics | Yes | Streamlined dimensions | Focus on executive metrics | Modified |
| Queue Utilization | Headline Ops KPI | No | Removed | Missing capacity data | Data Limitation |
| WFM Dashboard | Detailed WFM reporting | Yes | Realigned to vw_Workforce | Initial DAX errors | Implemented |
| Required vs Actual Headcount | Main canvas visual | No | Replaced by Demand Forecast | Redundant to Staffing Gap | Modified |
| Staffing Gap | Headline WFM KPI | Yes | Contextualized | Overlaps with Absentee metric | Modified |
| Absenteeism | Core WFM KPI | Yes | Standardized | Validated against model | Implemented |
| Planned Leave | Split shrinkage reporting | No | Merged into general shrinkage | Missing 'Planned' category | Data Limitation |
| Schedule Adherence | Core WFM KPI | Yes | None | Validated metric | Implemented |
| Occupancy | Core WFM KPI | Yes | Formula rewritten | Initial formula failed site test | Modified |
| Workforce Demand Forecast | Future AI state | Yes | Native PBI forecast used | Baseline predictive need | Modified |
| Capacity Risk | Headline predictive KPI | No | Retained as supporting metric | Logic skewed to 104% | Modified |
| Quality Dashboard | QA performance tracking | No | Deferred entirely | Scope reduction / speed to MVP | Deferred |
| Appeals Dashboard | Escalation & overturn rates | No | Deferred entirely | Scope reduction / speed to MVP | Deferred |
| Finance Dashboard | Full P&L / Cost tracking | No | Deferred entirely | Missing cost fields / Date errors | Deferred |
| Revenue Analysis | Financial tracking | No | Deferred | Tied to Finance dataset issues | Data Limitation |
| Profitability | Financial tracking | No | Deferred | Missing cost/margin fields | Data Limitation |
| Real-Time Visibility | Live operational streaming | No | Modeled conceptually | Outside MVP infrastructure scope | Future State |
| AI Forecasting | ML-driven predictions | No | PBI Baseline used | Data stability / ML complexity | Future State |
| Predictive Risk | Advanced ML risk flagging | No | Baseline risk mapped | Avoid overstating capabilities | Future State |

# 8. FINAL MVP SCOPE

CURRENT MVP:

Operations Analytics

Workforce Management

Workforce Demand Forecasting

Interactive Power BI analysis

SQL-backed data validation

DAX-based KPI calculations

Site-level workforce analysis

Tooltip-based contextual analysis

DEFERRED:

Quality Assurance dashboard

Appeals dashboard

Finance dashboard

Advanced AI/ML forecasting

Production predictive risk model

True real-time streaming / control tower

# 9. BUSINESS IMPACT OF THE CHANGES

The rigorous application of change control and requirement validation improved the project outcome in several key ways:

Reduced scope risk: Prevented the project from missing deadlines by focusing on core deliverables.

Prevented unsupported KPI calculations: Halted the deployment of metrics (like Queue Utilization and Planned Leave) that lacked data backing.

Improved data integrity: Caught and corrected the Occupancy calculation error before it influenced executive decision-making.

Avoided fabricated business metrics: Ensured the dashboard reflects reality rather than assumed operational states.

Increased analytical credibility: Maintained stakeholder trust by refusing to label a basic calculation as a complex 'Capacity Risk' indicator.

Added forward-looking demand forecasting: Delivered immediate predictive value without requiring heavy ML engineering.

Reduced dashboard redundancy: Replaced overlapping visuals with high-impact forecasting tools.

Improved WFM decision support: Delivered a highly accurate, DAX-validated workforce environment.

Created a stronger analytics case study: Demonstrated mature governance, critical thinking, and disciplined execution.

Preserved a roadmap: Set realistic expectations for future AI/ML and real-time capabilities.

Note: Deferred scope is not discarded. It remains documented in the project backlog for deployment in subsequent roadmap phases.

# 10. BUSINESS ANALYST CHANGE MANAGEMENT PERSPECTIVE

This project demonstrates several critical Business Analysis and Data Analytics lessons:

Requirements must be validated against actual data: A KPI should not be implemented simply because it exists in the BRD if the required source fields are unavailable or corrupted.

Data quality findings drive requirement changes: Discoveries (such as the Cebu workforce data gap or Finance date range anomalies) must actively trigger scope adjustments.

Scope must be aggressively controlled: When project timelines or data realities shift, the BA must prioritize depth and accuracy over superficial completion of all features.

Metrics require validation before promotion: A metric must survive mathematical validation across multiple dimensions (e.g., site-level Occupancy) before being presented to executives.

Predictive analytics should not be overstated: Be transparent about the difference between a baseline time-series forecast and a multivariate ML model.

Future-state architecture must be isolated from MVP: Clearly document what is built today versus what the architecture is designed to support tomorrow (e.g., real-time streaming).

Traceability is paramount: Every change must be traceable back to a specific business value proposition, technical constraint, or data limitation.

# 11. FUTURE ROADMAP

PHASE 1 — COMPLETED MVP

Operations Analytics

WFM

Demand Forecasting

DAX / Power BI semantic modeling

Tooltip analytics

PHASE 2 — ANALYTICAL EXPANSION

Quality Dashboard

Finance Dashboard

Appeals Dashboard

Improved capacity risk modeling

PHASE 3 — ADVANCED PREDICTIVE ANALYTICS

ML-based demand forecasting

Forecast accuracy measurement (MAE, RMSE, MAPE)

Predictive capacity risk

Anomaly detection

Scenario modeling

PHASE 4 — REAL-TIME CONTROL TOWER

Real-time data ingestion pipelines

Streaming operational KPIs

Automated alerts and triggers

Exception management

Cross-functional operational visibility