# Project Charter

# Document Control

| Document Name | Project Charter |
| --- | --- |
| Project | Trust & Safety Operations Intelligence & Workforce Performance Analytics |
| Organization | Enterprise Trust & Safety Operations Analytics |
| Version | 1.0 |
| Status | Draft |
| Prepared By | Tushar Mehta (Business Analyst) |
| Reviewed By | Director – Trust & Safety Operations |
| Approved By | Project Sponsor |
| Date | 28 June 2026 |

# Section 1 – Project Information

| Project Name | Trust & Safety Operations Intelligence & Workforce Performance Analytics |
| --- | --- |
| Organization | Enterprise Trust & Safety Operations Analytics |
| Project Sponsor | Director – Trust & Safety Operations |
| Business Analyst | Tushar Mehta |
| Project Methodology | Agile Scrum |
| Project Duration | 12 Weeks |
| Version | 1.0 |
| Document Status | Draft |

# Section 2 – Project Overview

## Project Background

Enterprise Trust & Safety Operations Analytics is a rapidly growing social media platform that reviews millions of pieces of user-generated content every day. Operational reporting is currently distributed across multiple Excel reports prepared by different departments, including Operations, Workforce Management, Quality Assurance, and Finance.

The absence of a centralized reporting platform makes it difficult for leadership to monitor operational performance, workforce utilization, SLA compliance, backlog, quality metrics, and billing performance. As a result, decision-making is delayed, manual effort is high, and operational risks are increasing.

To address these challenges, Enterprise Trust & Safety Operations Analytics is initiating the Trust & Safety Operations Intelligence & Workforce Performance Analytics project to deliver a centralized Business Intelligence solution using SQL, Excel, and Power BI.

# Section 3 – Business Problem Statement

Leadership currently relies on fragmented reports generated by multiple departments, resulting in inconsistent data, delayed reporting, limited operational visibility, and inefficient decision-making. The organization requires a centralized analytics platform that consolidates operational, workforce, quality, and billing data into actionable dashboards for strategic and operational decision-making.

# Section 4 – Business Objectives

The project aims to:

Centralize Trust & Safety operational reporting.

Improve visibility into SLA, backlog, occupancy, productivity, quality, and billing metrics.

Reduce manual reporting effort.

Enable faster and data-driven decision-making.

Improve workforce planning and capacity utilization.

Support leadership through executive dashboards and operational insights.

# Section 5 – Scope Definitions

## In Scope

Development of a consolidated SQL database/data mart to house cross-departmental metrics.

Design and deployment of interactive Power BI dashboards tailored for Executive, Operations, and WFM personas.

Integration of key data streams: Operations, WFM, QA, and Finance.

## Out of Scope

Modifications to Enterprise Trust & Safety Operations Analytics’ primary content moderation platform/user interface.

Deployment of predictive Machine Learning models.

Direct system changes to core HRIS or internal Payroll platforms.

# Section 6 – High-Level Timeline

| Project Phase / Milestone | Estimated Schedule |
| --- | --- |
| Sprint 1-2: Requirements Gathering | Weeks 1 - 2 |
| Sprint 3-6: Data Architecture | Weeks 3 - 6 |
| Sprint 7-9: Dashboard Development | Weeks 7 - 9 |
| Sprint 10-11: UAT & QA | Weeks 10 - 11 |
| Sprint 12: Deployment & Handover | Week 12 |

# Section 7 – Key Stakeholders

| Role | Department | Responsibility |
| --- | --- | --- |
| Project Sponsor | Trust & Safety Ops | Approves funding and scope. |
| Business Analyst | Data / Analytics | Requirements documentation. |
| WFM Manager | Workforce Management | SME inputs on capacity. |
| QA Lead | Quality Assurance | Defines quality metrics. |
| Data Engineer | IT / Engineering | Data pipeline integrations. |

# Section 8 – Success Criteria

Reduce manual report preparation time by at least 70%.

Achieve a single source of truth for Operations, WFM, QA, and Finance reporting.

Improve leadership reporting turnaround from multiple Excel reports to centralized Power BI dashboards.

Enable monitoring of all critical operational KPIs through one integrated reporting platform.

Improve decision-making for staffing, capacity planning, SLA compliance, and billing.

# Section 9 – Assumptions

Required operational data will be available from source systems.

Business stakeholders will be available for requirement workshops.

Existing Microsoft ecosystem (Excel, SQL, Power BI) will be used.

Data definitions across departments will be standardized during analysis.

Project follows Agile Scrum methodology.

# Section 10 – Constraints

Project duration is limited to 12 weeks.

Existing technology stack must be utilized.

No modifications to production moderation systems.

Dashboard performance should support leadership reporting.

Project scope excludes predictive AI/ML in Phase 1.

# Section 11 – Initial Risk Register

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Inconsistent data across departments | High | Define common KPI dictionary |
| Delayed stakeholder feedback | Medium | Weekly requirement workshops |
| Data quality issues | High | Validation and cleansing before reporting |
| Scope creep | High | Formal change request process |
| Missing historical data | Medium | Identify gaps during data profiling |

# Section 12 – Approval Matrix

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor | Director – Trust & Safety |  |  |
| Business Analyst | Tushar Mehta |  |  |