## Product Backlog
Story ID | Epic ID | Epic Name | Feature ID | Feature Name | Story Title | Story Summary | Business Objective | Priority (MoSCoW) | Business Value | Story Points | Sprint | Release | Story Status | Assigned Team | Business Owner | Product Owner | Dependency | Related Dashboard | Related KPI | Related BRD | Related FRD | Acceptance Criteria Status | Definition of Done Status | Target Sprint | Actual Sprint | Remarks
US-001 | EP-01 | Executive Analytics | FT-001 | Executive Dashboard | Executive Dashboard - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable executive dashboard capabilities. | Must Have | Medium | 5 | Sprint 1 | Release 1.0 | Done | BI Dev Team | VP Operations | PO Team | Data Ingestion | Executive Dash | N/A | BRD-01 | FRD-01 | Defined | Met | Sprint 1 | Sprint 1
US-002 | EP-01 | Executive Analytics | FT-001 | Executive Dashboard | Executive Dashboard - DAX Measures | Develop core DAX calculations for KPIs. | Enable executive dashboard capabilities. | Must Have | High | 3 | Sprint 2 | Release 1.0 | In Progress | BI Dev Team | VP Operations | PO Team | None | Executive Dash | Multiple | BRD-01 | FRD-01 | Defined | Pending | Sprint 2 | TBD
US-003 | EP-01 | Executive Analytics | FT-001 | Executive Dashboard | Executive Dashboard - Visual Layout | Design the frontend visuals and report page layout. | Enable executive dashboard capabilities. | Must Have | High | 5 | Sprint 3 | Release 1.0 | Ready for Development | BI Dev Team | VP Operations | PO Team | None | Executive Dash | N/A | BRD-01 | FRD-01 | Defined | Pending | Sprint 3 | TBD
US-004 | EP-01 | Executive Analytics | FT-001 | Executive Dashboard | Executive Dashboard - RLS Implementation | Apply role-based security to the data domain. | Enable executive dashboard capabilities. | Must Have | High | 2 | Sprint 4 | Release 1.0 | Ready for Refinement | BI Dev Team | VP Operations | PO Team | None | Executive Dash | N/A | BRD-01 | FRD-01 | Pending | Pending | Sprint 4 | TBD
US-005 | EP-01 | Executive Analytics | FT-002 | Executive KPI Monitoring | Executive KPI Monitoring - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable executive kpi monitoring capabilities. | Must Have | Medium | 5 | Sprint 1 | Release 1.0 | Done | BI Dev Team | VP Operations | PO Team | Data Ingestion | Executive Dash | N/A | BRD-01 | FRD-01 | Defined | Met | Sprint 1 | Sprint 1
US-006 | EP-01 | Executive Analytics | FT-002 | Executive KPI Monitoring | Executive KPI Monitoring - DAX Measures | Develop core DAX calculations for KPIs. | Enable executive kpi monitoring capabilities. | Must Have | High | 3 | Sprint 2 | Release 1.0 | In Progress | BI Dev Team | VP Operations | PO Team | None | Executive Dash | Multiple | BRD-01 | FRD-01 | Defined | Pending | Sprint 2 | TBD
US-007 | EP-01 | Executive Analytics | FT-002 | Executive KPI Monitoring | Executive KPI Monitoring - Visual Layout | Design the frontend visuals and report page layout. | Enable executive kpi monitoring capabilities. | Must Have | High | 5 | Sprint 3 | Release 1.0 | Ready for Development | BI Dev Team | VP Operations | PO Team | None | Executive Dash | N/A | BRD-01 | FRD-01 | Defined | Pending | Sprint 3 | TBD
US-008 | EP-01 | Executive Analytics | FT-002 | Executive KPI Monitoring | Executive KPI Monitoring - RLS Implementation | Apply role-based security to the data domain. | Enable executive kpi monitoring capabilities. | Must Have | High | 2 | Sprint 4 | Release 1.0 | Ready for Refinement | BI Dev Team | VP Operations | PO Team | None | Executive Dash | N/A | BRD-01 | FRD-01 | Pending | Pending | Sprint 4 | TBD
US-009 | EP-01 | Executive Analytics | FT-005 | Executive Dashboard Filters | Executive Dashboard Filters - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable executive dashboard filters capabilities. | Must Have | Medium | 5 | Sprint 1 | Release 1.0 | Done | BI Dev Team | VP Operations | PO Team | Data Ingestion | Executive Dash | N/A | BRD-01 | FRD-01 | Defined | Met | Sprint 1 | Sprint 1
US-010 | EP-01 | Executive Analytics | FT-005 | Executive Dashboard Filters | Executive Dashboard Filters - DAX Measures | Develop core DAX calculations for KPIs. | Enable executive dashboard filters capabilities. | Must Have | High | 3 | Sprint 2 | Release 1.0 | In Progress | BI Dev Team | VP Operations | PO Team | None | Executive Dash | Multiple | BRD-01 | FRD-01 | Defined | Pending | Sprint 2 | TBD
US-011 | EP-01 | Executive Analytics | FT-005 | Executive Dashboard Filters | Executive Dashboard Filters - Visual Layout | Design the frontend visuals and report page layout. | Enable executive dashboard filters capabilities. | Must Have | High | 5 | Sprint 3 | Release 1.0 | Ready for Development | BI Dev Team | VP Operations | PO Team | None | Executive Dash | N/A | BRD-01 | FRD-01 | Defined | Pending | Sprint 3 | TBD
US-012 | EP-01 | Executive Analytics | FT-005 | Executive Dashboard Filters | Executive Dashboard Filters - RLS Implementation | Apply role-based security to the data domain. | Enable executive dashboard filters capabilities. | Must Have | High | 2 | Sprint 4 | Release 1.0 | Ready for Refinement | BI Dev Team | VP Operations | PO Team | None | Executive Dash | N/A | BRD-01 | FRD-01 | Pending | Pending | Sprint 4 | TBD
US-013 | EP-01 | Executive Analytics | FT-006 | Executive Dashboard Export | Executive Dashboard Export - DAX Measures | Develop core DAX calculations for KPIs. | Enable executive dashboard export capabilities. | Should Have | High | 3 | Backlog | Release 1.1 | Draft | BI Dev Team | VP Operations | PO Team | None | Executive Dash | Multiple | BRD-01 | FRD-01 | Pending | Pending | Backlog | TBD
US-014 | EP-01 | Executive Analytics | FT-006 | Executive Dashboard Export | Executive Dashboard Export - Visual Layout | Design the frontend visuals and report page layout. | Enable executive dashboard export capabilities. | Should Have | High | 5 | Backlog | Release 1.1 | Draft | BI Dev Team | VP Operations | PO Team | None | Executive Dash | N/A | BRD-01 | FRD-01 | Pending | Pending | Backlog | TBD
US-015 | EP-02 | Operations Analytics | FT-008 | Queue Performance Monitoring | Queue Performance Monitoring - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable queue performance monitoring capabilities. | Must Have | Medium | 5 | Sprint 1 | Release 1.0 | Done | BI Dev Team | Dir of Operations | PO Team | Data Ingestion | Operations Dash | N/A | BRD-02 | FRD-02 | Defined | Met | Sprint 1 | Sprint 1
US-016 | EP-02 | Operations Analytics | FT-008 | Queue Performance Monitoring | Queue Performance Monitoring - DAX Measures | Develop core DAX calculations for KPIs. | Enable queue performance monitoring capabilities. | Must Have | High | 3 | Sprint 2 | Release 1.0 | In Progress | BI Dev Team | Dir of Operations | PO Team | None | Operations Dash | Multiple | BRD-02 | FRD-02 | Defined | Pending | Sprint 2 | TBD
US-017 | EP-02 | Operations Analytics | FT-008 | Queue Performance Monitoring | Queue Performance Monitoring - Visual Layout | Design the frontend visuals and report page layout. | Enable queue performance monitoring capabilities. | Must Have | High | 5 | Sprint 3 | Release 1.0 | Ready for Development | BI Dev Team | Dir of Operations | PO Team | None | Operations Dash | N/A | BRD-02 | FRD-02 | Defined | Pending | Sprint 3 | TBD
US-018 | EP-02 | Operations Analytics | FT-008 | Queue Performance Monitoring | Queue Performance Monitoring - RLS Implementation | Apply role-based security to the data domain. | Enable queue performance monitoring capabilities. | Must Have | High | 2 | Sprint 4 | Release 1.0 | Ready for Refinement | BI Dev Team | Dir of Operations | PO Team | None | Operations Dash | N/A | BRD-02 | FRD-02 | Pending | Pending | Sprint 4 | TBD
US-019 | EP-02 | Operations Analytics | FT-009 | SLA Monitoring | SLA Monitoring - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable sla monitoring capabilities. | Must Have | Medium | 5 | Sprint 1 | Release 1.0 | Done | BI Dev Team | Dir of Operations | PO Team | Data Ingestion | Operations Dash | N/A | BRD-02 | FRD-02 | Defined | Met | Sprint 1 | Sprint 1
US-020 | EP-02 | Operations Analytics | FT-009 | SLA Monitoring | SLA Monitoring - DAX Measures | Develop core DAX calculations for KPIs. | Enable sla monitoring capabilities. | Must Have | High | 3 | Sprint 2 | Release 1.0 | In Progress | BI Dev Team | Dir of Operations | PO Team | None | Operations Dash | Multiple | BRD-02 | FRD-02 | Defined | Pending | Sprint 2 | TBD
US-021 | EP-02 | Operations Analytics | FT-009 | SLA Monitoring | SLA Monitoring - Visual Layout | Design the frontend visuals and report page layout. | Enable sla monitoring capabilities. | Must Have | High | 5 | Sprint 3 | Release 1.0 | Ready for Development | BI Dev Team | Dir of Operations | PO Team | None | Operations Dash | N/A | BRD-02 | FRD-02 | Defined | Pending | Sprint 3 | TBD
US-022 | EP-02 | Operations Analytics | FT-009 | SLA Monitoring | SLA Monitoring - RLS Implementation | Apply role-based security to the data domain. | Enable sla monitoring capabilities. | Must Have | High | 2 | Sprint 4 | Release 1.0 | Ready for Refinement | BI Dev Team | Dir of Operations | PO Team | None | Operations Dash | N/A | BRD-02 | FRD-02 | Pending | Pending | Sprint 4 | TBD
US-023 | EP-02 | Operations Analytics | FT-010 | Productivity Analysis | Productivity Analysis - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable productivity analysis capabilities. | Must Have | Medium | 5 | Sprint 1 | Release 1.0 | Done | BI Dev Team | Dir of Operations | PO Team | Data Ingestion | Operations Dash | N/A | BRD-02 | FRD-02 | Defined | Met | Sprint 1 | Sprint 1
US-024 | EP-02 | Operations Analytics | FT-010 | Productivity Analysis | Productivity Analysis - DAX Measures | Develop core DAX calculations for KPIs. | Enable productivity analysis capabilities. | Must Have | High | 3 | Sprint 2 | Release 1.0 | In Progress | BI Dev Team | Dir of Operations | PO Team | None | Operations Dash | Multiple | BRD-02 | FRD-02 | Defined | Pending | Sprint 2 | TBD
US-025 | EP-02 | Operations Analytics | FT-010 | Productivity Analysis | Productivity Analysis - Visual Layout | Design the frontend visuals and report page layout. | Enable productivity analysis capabilities. | Must Have | High | 5 | Sprint 3 | Release 1.0 | Ready for Development | BI Dev Team | Dir of Operations | PO Team | None | Operations Dash | N/A | BRD-02 | FRD-02 | Defined | Pending | Sprint 3 | TBD
US-026 | EP-02 | Operations Analytics | FT-010 | Productivity Analysis | Productivity Analysis - RLS Implementation | Apply role-based security to the data domain. | Enable productivity analysis capabilities. | Must Have | High | 2 | Sprint 4 | Release 1.0 | Ready for Refinement | BI Dev Team | Dir of Operations | PO Team | None | Operations Dash | N/A | BRD-02 | FRD-02 | Pending | Pending | Sprint 4 | TBD
US-027 | EP-02 | Operations Analytics | FT-012 | Operational Trend Analysis | Operational Trend Analysis - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable operational trend analysis capabilities. | Must Have | Medium | 5 | Backlog | Release 1.1 | Draft | BI Dev Team | Dir of Operations | PO Team | Data Ingestion | Operations Dash | N/A | BRD-02 | FRD-02 | Pending | Pending | Backlog | TBD
US-028 | EP-02 | Operations Analytics | FT-012 | Operational Trend Analysis | Operational Trend Analysis - DAX Measures | Develop core DAX calculations for KPIs. | Enable operational trend analysis capabilities. | Must Have | High | 3 | Backlog | Release 1.1 | Draft | BI Dev Team | Dir of Operations | PO Team | None | Operations Dash | Multiple | BRD-02 | FRD-02 | Pending | Pending | Backlog | TBD
US-029 | EP-02 | Operations Analytics | FT-012 | Operational Trend Analysis | Operational Trend Analysis - Visual Layout | Design the frontend visuals and report page layout. | Enable operational trend analysis capabilities. | Must Have | High | 5 | Backlog | Release 1.1 | Draft | BI Dev Team | Dir of Operations | PO Team | None | Operations Dash | N/A | BRD-02 | FRD-02 | Pending | Pending | Backlog | TBD
US-030 | EP-02 | Operations Analytics | FT-012 | Operational Trend Analysis | Operational Trend Analysis - RLS Implementation | Apply role-based security to the data domain. | Enable operational trend analysis capabilities. | Must Have | High | 2 | Backlog | Release 1.1 | Draft | BI Dev Team | Dir of Operations | PO Team | None | Operations Dash | N/A | BRD-02 | FRD-02 | Pending | Pending | Backlog | TBD
US-031 | EP-03 | Quality Analytics | FT-015 | QA Dashboard | QA Dashboard - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable qa dashboard capabilities. | Must Have | Medium | 5 | Sprint 1 | Release 1.0 | Done | BI Dev Team | Global QA Manager | PO Team | Data Ingestion | Quality Dash | N/A | BRD-03 | FRD-03 | Defined | Met | Sprint 1 | Sprint 1
US-032 | EP-03 | Quality Analytics | FT-015 | QA Dashboard | QA Dashboard - DAX Measures | Develop core DAX calculations for KPIs. | Enable qa dashboard capabilities. | Must Have | High | 3 | Sprint 2 | Release 1.0 | In Progress | BI Dev Team | Global QA Manager | PO Team | None | Quality Dash | Multiple | BRD-03 | FRD-03 | Defined | Pending | Sprint 2 | TBD
US-033 | EP-03 | Quality Analytics | FT-015 | QA Dashboard | QA Dashboard - Visual Layout | Design the frontend visuals and report page layout. | Enable qa dashboard capabilities. | Must Have | High | 5 | Sprint 3 | Release 1.0 | Ready for Development | BI Dev Team | Global QA Manager | PO Team | None | Quality Dash | N/A | BRD-03 | FRD-03 | Defined | Pending | Sprint 3 | TBD
US-034 | EP-03 | Quality Analytics | FT-015 | QA Dashboard | QA Dashboard - RLS Implementation | Apply role-based security to the data domain. | Enable qa dashboard capabilities. | Must Have | High | 2 | Sprint 4 | Release 1.0 | Ready for Refinement | BI Dev Team | Global QA Manager | PO Team | None | Quality Dash | N/A | BRD-03 | FRD-03 | Pending | Pending | Sprint 4 | TBD
US-035 | EP-03 | Quality Analytics | FT-017 | Error Category Analysis | Error Category Analysis - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable error category analysis capabilities. | Must Have | Medium | 5 | Sprint 1 | Release 1.0 | Done | BI Dev Team | Global QA Manager | PO Team | Data Ingestion | Quality Dash | N/A | BRD-03 | FRD-03 | Defined | Met | Sprint 1 | Sprint 1
US-036 | EP-03 | Quality Analytics | FT-017 | Error Category Analysis | Error Category Analysis - DAX Measures | Develop core DAX calculations for KPIs. | Enable error category analysis capabilities. | Must Have | High | 3 | Sprint 2 | Release 1.0 | In Progress | BI Dev Team | Global QA Manager | PO Team | None | Quality Dash | Multiple | BRD-03 | FRD-03 | Defined | Pending | Sprint 2 | TBD
US-037 | EP-03 | Quality Analytics | FT-017 | Error Category Analysis | Error Category Analysis - Visual Layout | Design the frontend visuals and report page layout. | Enable error category analysis capabilities. | Must Have | High | 5 | Sprint 3 | Release 1.0 | Ready for Development | BI Dev Team | Global QA Manager | PO Team | None | Quality Dash | N/A | BRD-03 | FRD-03 | Defined | Pending | Sprint 3 | TBD
US-038 | EP-03 | Quality Analytics | FT-017 | Error Category Analysis | Error Category Analysis - RLS Implementation | Apply role-based security to the data domain. | Enable error category analysis capabilities. | Must Have | High | 2 | Sprint 4 | Release 1.0 | Ready for Refinement | BI Dev Team | Global QA Manager | PO Team | None | Quality Dash | N/A | BRD-03 | FRD-03 | Pending | Pending | Sprint 4 | TBD
US-039 | EP-03 | Quality Analytics | FT-019 | QA Trend Analysis | QA Trend Analysis - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable qa trend analysis capabilities. | Must Have | Medium | 5 | Backlog | Release 1.1 | Draft | BI Dev Team | Global QA Manager | PO Team | Data Ingestion | Quality Dash | N/A | BRD-03 | FRD-03 | Pending | Pending | Backlog | TBD
US-040 | EP-03 | Quality Analytics | FT-019 | QA Trend Analysis | QA Trend Analysis - DAX Measures | Develop core DAX calculations for KPIs. | Enable qa trend analysis capabilities. | Must Have | High | 3 | Backlog | Release 1.1 | Draft | BI Dev Team | Global QA Manager | PO Team | None | Quality Dash | Multiple | BRD-03 | FRD-03 | Pending | Pending | Backlog | TBD
US-041 | EP-03 | Quality Analytics | FT-019 | QA Trend Analysis | QA Trend Analysis - Visual Layout | Design the frontend visuals and report page layout. | Enable qa trend analysis capabilities. | Must Have | High | 5 | Backlog | Release 1.1 | Draft | BI Dev Team | Global QA Manager | PO Team | None | Quality Dash | N/A | BRD-03 | FRD-03 | Pending | Pending | Backlog | TBD
US-042 | EP-03 | Quality Analytics | FT-019 | QA Trend Analysis | QA Trend Analysis - RLS Implementation | Apply role-based security to the data domain. | Enable qa trend analysis capabilities. | Must Have | High | 2 | Backlog | Release 1.1 | Draft | BI Dev Team | Global QA Manager | PO Team | None | Quality Dash | N/A | BRD-03 | FRD-03 | Pending | Pending | Backlog | TBD
US-043 | EP-04 | Workforce Analytics | FT-021 | Staffing Overview | Staffing Overview - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable staffing overview capabilities. | Must Have | Medium | 5 | Sprint 1 | Release 1.0 | Done | BI Dev Team | Dir of WFM | PO Team | Data Ingestion | Workforce Dash | N/A | BRD-04 | FRD-04 | Defined | Met | Sprint 1 | Sprint 1
US-044 | EP-04 | Workforce Analytics | FT-021 | Staffing Overview | Staffing Overview - DAX Measures | Develop core DAX calculations for KPIs. | Enable staffing overview capabilities. | Must Have | High | 3 | Sprint 2 | Release 1.0 | In Progress | BI Dev Team | Dir of WFM | PO Team | None | Workforce Dash | Multiple | BRD-04 | FRD-04 | Defined | Pending | Sprint 2 | TBD
US-045 | EP-04 | Workforce Analytics | FT-021 | Staffing Overview | Staffing Overview - Visual Layout | Design the frontend visuals and report page layout. | Enable staffing overview capabilities. | Must Have | High | 5 | Sprint 3 | Release 1.0 | Ready for Development | BI Dev Team | Dir of WFM | PO Team | None | Workforce Dash | N/A | BRD-04 | FRD-04 | Defined | Pending | Sprint 3 | TBD
US-046 | EP-04 | Workforce Analytics | FT-021 | Staffing Overview | Staffing Overview - RLS Implementation | Apply role-based security to the data domain. | Enable staffing overview capabilities. | Must Have | High | 2 | Sprint 4 | Release 1.0 | Ready for Refinement | BI Dev Team | Dir of WFM | PO Team | None | Workforce Dash | N/A | BRD-04 | FRD-04 | Pending | Pending | Sprint 4 | TBD
US-047 | EP-04 | Workforce Analytics | FT-022 | Occupancy Monitoring | Occupancy Monitoring - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable occupancy monitoring capabilities. | Must Have | Medium | 5 | Sprint 1 | Release 1.0 | Done | BI Dev Team | Dir of WFM | PO Team | Data Ingestion | Workforce Dash | N/A | BRD-04 | FRD-04 | Defined | Met | Sprint 1 | Sprint 1
US-048 | EP-04 | Workforce Analytics | FT-022 | Occupancy Monitoring | Occupancy Monitoring - DAX Measures | Develop core DAX calculations for KPIs. | Enable occupancy monitoring capabilities. | Must Have | High | 3 | Sprint 2 | Release 1.0 | In Progress | BI Dev Team | Dir of WFM | PO Team | None | Workforce Dash | Multiple | BRD-04 | FRD-04 | Defined | Pending | Sprint 2 | TBD
US-049 | EP-04 | Workforce Analytics | FT-022 | Occupancy Monitoring | Occupancy Monitoring - Visual Layout | Design the frontend visuals and report page layout. | Enable occupancy monitoring capabilities. | Must Have | High | 5 | Sprint 3 | Release 1.0 | Ready for Development | BI Dev Team | Dir of WFM | PO Team | None | Workforce Dash | N/A | BRD-04 | FRD-04 | Defined | Pending | Sprint 3 | TBD
US-050 | EP-04 | Workforce Analytics | FT-022 | Occupancy Monitoring | Occupancy Monitoring - RLS Implementation | Apply role-based security to the data domain. | Enable occupancy monitoring capabilities. | Must Have | High | 2 | Sprint 4 | Release 1.0 | Ready for Refinement | BI Dev Team | Dir of WFM | PO Team | None | Workforce Dash | N/A | BRD-04 | FRD-04 | Pending | Pending | Sprint 4 | TBD
US-051 | EP-04 | Workforce Analytics | FT-024 | Shrinkage Analysis | Shrinkage Analysis - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable shrinkage analysis capabilities. | Must Have | Medium | 5 | Backlog | Release 1.1 | Draft | BI Dev Team | Dir of WFM | PO Team | Data Ingestion | Workforce Dash | N/A | BRD-04 | FRD-04 | Pending | Pending | Backlog | TBD
US-052 | EP-04 | Workforce Analytics | FT-024 | Shrinkage Analysis | Shrinkage Analysis - DAX Measures | Develop core DAX calculations for KPIs. | Enable shrinkage analysis capabilities. | Must Have | High | 3 | Backlog | Release 1.1 | Draft | BI Dev Team | Dir of WFM | PO Team | None | Workforce Dash | Multiple | BRD-04 | FRD-04 | Pending | Pending | Backlog | TBD
US-053 | EP-04 | Workforce Analytics | FT-024 | Shrinkage Analysis | Shrinkage Analysis - Visual Layout | Design the frontend visuals and report page layout. | Enable shrinkage analysis capabilities. | Must Have | High | 5 | Backlog | Release 1.1 | Draft | BI Dev Team | Dir of WFM | PO Team | None | Workforce Dash | N/A | BRD-04 | FRD-04 | Pending | Pending | Backlog | TBD
US-054 | EP-04 | Workforce Analytics | FT-024 | Shrinkage Analysis | Shrinkage Analysis - RLS Implementation | Apply role-based security to the data domain. | Enable shrinkage analysis capabilities. | Must Have | High | 2 | Backlog | Release 1.1 | Draft | BI Dev Team | Dir of WFM | PO Team | None | Workforce Dash | N/A | BRD-04 | FRD-04 | Pending | Pending | Backlog | TBD
US-055 | EP-05 | Appeals Analytics | FT-027 | Appeals Dashboard | Appeals Dashboard - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable appeals dashboard capabilities. | Must Have | Medium | 5 | Sprint 1 | Release 1.0 | Done | BI Dev Team | Policy Director | PO Team | Data Ingestion | Appeals Dash | N/A | BRD-05 | FRD-05 | Defined | Met | Sprint 1 | Sprint 1
US-056 | EP-05 | Appeals Analytics | FT-027 | Appeals Dashboard | Appeals Dashboard - DAX Measures | Develop core DAX calculations for KPIs. | Enable appeals dashboard capabilities. | Must Have | High | 3 | Sprint 2 | Release 1.0 | In Progress | BI Dev Team | Policy Director | PO Team | None | Appeals Dash | Multiple | BRD-05 | FRD-05 | Defined | Pending | Sprint 2 | TBD
US-057 | EP-05 | Appeals Analytics | FT-027 | Appeals Dashboard | Appeals Dashboard - Visual Layout | Design the frontend visuals and report page layout. | Enable appeals dashboard capabilities. | Must Have | High | 5 | Sprint 3 | Release 1.0 | Ready for Development | BI Dev Team | Policy Director | PO Team | None | Appeals Dash | N/A | BRD-05 | FRD-05 | Defined | Pending | Sprint 3 | TBD
US-058 | EP-05 | Appeals Analytics | FT-027 | Appeals Dashboard | Appeals Dashboard - RLS Implementation | Apply role-based security to the data domain. | Enable appeals dashboard capabilities. | Must Have | High | 2 | Sprint 4 | Release 1.0 | Ready for Refinement | BI Dev Team | Policy Director | PO Team | None | Appeals Dash | N/A | BRD-05 | FRD-05 | Pending | Pending | Sprint 4 | TBD
US-059 | EP-05 | Appeals Analytics | FT-028 | Appeals Intake | Appeals Intake - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable appeals intake capabilities. | Must Have | Medium | 5 | Sprint 1 | Release 1.0 | Done | BI Dev Team | Policy Director | PO Team | Data Ingestion | Appeals Dash | N/A | BRD-05 | FRD-05 | Defined | Met | Sprint 1 | Sprint 1
US-060 | EP-05 | Appeals Analytics | FT-028 | Appeals Intake | Appeals Intake - DAX Measures | Develop core DAX calculations for KPIs. | Enable appeals intake capabilities. | Must Have | High | 3 | Sprint 2 | Release 1.0 | In Progress | BI Dev Team | Policy Director | PO Team | None | Appeals Dash | Multiple | BRD-05 | FRD-05 | Defined | Pending | Sprint 2 | TBD
US-061 | EP-05 | Appeals Analytics | FT-028 | Appeals Intake | Appeals Intake - Visual Layout | Design the frontend visuals and report page layout. | Enable appeals intake capabilities. | Must Have | High | 5 | Sprint 3 | Release 1.0 | Ready for Development | BI Dev Team | Policy Director | PO Team | None | Appeals Dash | N/A | BRD-05 | FRD-05 | Defined | Pending | Sprint 3 | TBD
US-062 | EP-05 | Appeals Analytics | FT-028 | Appeals Intake | Appeals Intake - RLS Implementation | Apply role-based security to the data domain. | Enable appeals intake capabilities. | Must Have | High | 2 | Sprint 4 | Release 1.0 | Ready for Refinement | BI Dev Team | Policy Director | PO Team | None | Appeals Dash | N/A | BRD-05 | FRD-05 | Pending | Pending | Sprint 4 | TBD
US-063 | EP-05 | Appeals Analytics | FT-031 | Overturn Rate Analysis | Overturn Rate Analysis - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable overturn rate analysis capabilities. | Must Have | Medium | 5 | Backlog | Release 1.1 | Draft | BI Dev Team | Policy Director | PO Team | Data Ingestion | Appeals Dash | N/A | BRD-05 | FRD-05 | Pending | Pending | Backlog | TBD
US-064 | EP-05 | Appeals Analytics | FT-031 | Overturn Rate Analysis | Overturn Rate Analysis - DAX Measures | Develop core DAX calculations for KPIs. | Enable overturn rate analysis capabilities. | Must Have | High | 3 | Backlog | Release 1.1 | Draft | BI Dev Team | Policy Director | PO Team | None | Appeals Dash | Multiple | BRD-05 | FRD-05 | Pending | Pending | Backlog | TBD
US-065 | EP-05 | Appeals Analytics | FT-031 | Overturn Rate Analysis | Overturn Rate Analysis - Visual Layout | Design the frontend visuals and report page layout. | Enable overturn rate analysis capabilities. | Must Have | High | 5 | Backlog | Release 1.1 | Draft | BI Dev Team | Policy Director | PO Team | None | Appeals Dash | N/A | BRD-05 | FRD-05 | Pending | Pending | Backlog | TBD
US-066 | EP-05 | Appeals Analytics | FT-031 | Overturn Rate Analysis | Overturn Rate Analysis - RLS Implementation | Apply role-based security to the data domain. | Enable overturn rate analysis capabilities. | Must Have | High | 2 | Backlog | Release 1.1 | Draft | BI Dev Team | Policy Director | PO Team | None | Appeals Dash | N/A | BRD-05 | FRD-05 | Pending | Pending | Backlog | TBD
US-067 | EP-06 | Financial Analytics | FT-033 | Revenue Dashboard | Revenue Dashboard - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable revenue dashboard capabilities. | Must Have | Medium | 5 | Sprint 1 | Release 1.0 | Done | BI Dev Team | Dir of Finance | PO Team | Data Ingestion | Financial Dash | N/A | BRD-06 | FRD-06 | Defined | Met | Sprint 1 | Sprint 1
US-068 | EP-06 | Financial Analytics | FT-033 | Revenue Dashboard | Revenue Dashboard - DAX Measures | Develop core DAX calculations for KPIs. | Enable revenue dashboard capabilities. | Must Have | High | 3 | Sprint 2 | Release 1.0 | In Progress | BI Dev Team | Dir of Finance | PO Team | None | Financial Dash | Multiple | BRD-06 | FRD-06 | Defined | Pending | Sprint 2 | TBD
US-069 | EP-06 | Financial Analytics | FT-033 | Revenue Dashboard | Revenue Dashboard - Visual Layout | Design the frontend visuals and report page layout. | Enable revenue dashboard capabilities. | Must Have | High | 5 | Sprint 3 | Release 1.0 | Ready for Development | BI Dev Team | Dir of Finance | PO Team | None | Financial Dash | N/A | BRD-06 | FRD-06 | Defined | Pending | Sprint 3 | TBD
US-070 | EP-06 | Financial Analytics | FT-033 | Revenue Dashboard | Revenue Dashboard - RLS Implementation | Apply role-based security to the data domain. | Enable revenue dashboard capabilities. | Must Have | High | 2 | Sprint 4 | Release 1.0 | Ready for Refinement | BI Dev Team | Dir of Finance | PO Team | None | Financial Dash | N/A | BRD-06 | FRD-06 | Pending | Pending | Sprint 4 | TBD
US-071 | EP-06 | Financial Analytics | FT-035 | Billing Attainment | Billing Attainment - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable billing attainment capabilities. | Must Have | Medium | 5 | Sprint 1 | Release 1.0 | Done | BI Dev Team | Dir of Finance | PO Team | Data Ingestion | Financial Dash | N/A | BRD-06 | FRD-06 | Defined | Met | Sprint 1 | Sprint 1
US-072 | EP-06 | Financial Analytics | FT-035 | Billing Attainment | Billing Attainment - DAX Measures | Develop core DAX calculations for KPIs. | Enable billing attainment capabilities. | Must Have | High | 3 | Sprint 2 | Release 1.0 | In Progress | BI Dev Team | Dir of Finance | PO Team | None | Financial Dash | Multiple | BRD-06 | FRD-06 | Defined | Pending | Sprint 2 | TBD
US-073 | EP-06 | Financial Analytics | FT-035 | Billing Attainment | Billing Attainment - Visual Layout | Design the frontend visuals and report page layout. | Enable billing attainment capabilities. | Must Have | High | 5 | Sprint 3 | Release 1.0 | Ready for Development | BI Dev Team | Dir of Finance | PO Team | None | Financial Dash | N/A | BRD-06 | FRD-06 | Defined | Pending | Sprint 3 | TBD
US-074 | EP-06 | Financial Analytics | FT-035 | Billing Attainment | Billing Attainment - RLS Implementation | Apply role-based security to the data domain. | Enable billing attainment capabilities. | Must Have | High | 2 | Sprint 4 | Release 1.0 | Ready for Refinement | BI Dev Team | Dir of Finance | PO Team | None | Financial Dash | N/A | BRD-06 | FRD-06 | Pending | Pending | Sprint 4 | TBD
US-075 | EP-06 | Financial Analytics | FT-038 | Margin Analysis | Margin Analysis - UI Data Modeling | Create the underlying semantic model and table relationships. | Enable margin analysis capabilities. | Must Have | Medium | 5 | Backlog | Release 1.1 | Draft | BI Dev Team | Dir of Finance | PO Team | Data Ingestion | Financial Dash | N/A | BRD-06 | FRD-06 | Pending | Pending | Backlog | TBD
US-076 | EP-06 | Financial Analytics | FT-038 | Margin Analysis | Margin Analysis - DAX Measures | Develop core DAX calculations for KPIs. | Enable margin analysis capabilities. | Must Have | High | 3 | Backlog | Release 1.1 | Draft | BI Dev Team | Dir of Finance | PO Team | None | Financial Dash | Multiple | BRD-06 | FRD-06 | Pending | Pending | Backlog | TBD
US-077 | EP-06 | Financial Analytics | FT-038 | Margin Analysis | Margin Analysis - Visual Layout | Design the frontend visuals and report page layout. | Enable margin analysis capabilities. | Must Have | High | 5 | Backlog | Release 1.1 | Draft | BI Dev Team | Dir of Finance | PO Team | None | Financial Dash | N/A | BRD-06 | FRD-06 | Pending | Pending | Backlog | TBD
US-078 | EP-06 | Financial Analytics | FT-038 | Margin Analysis | Margin Analysis - RLS Implementation | Apply role-based security to the data domain. | Enable margin analysis capabilities. | Must Have | High | 2 | Backlog | Release 1.1 | Draft | BI Dev Team | Dir of Finance | PO Team | None | Financial Dash | N/A | BRD-06 | FRD-06 | Pending | Pending | Backlog | TBD

## Epic Summary
Epic ID | Epic Name | Business Purpose | Number of Features | Number of Stories | Priority | Business Owner | Status
EP-01 | Executive Analytics | Strategic Analytics | 4 | 14 | Must Have | VP Operations | In Progress
EP-02 | Operations Analytics | Strategic Analytics | 4 | 16 | Must Have | Dir of Operations | In Progress
EP-03 | Quality Analytics | Strategic Analytics | 3 | 12 | Must Have | Global QA Manager | In Progress
EP-04 | Workforce Analytics | Strategic Analytics | 3 | 12 | Must Have | Dir of WFM | In Progress
EP-05 | Appeals Analytics | Strategic Analytics | 3 | 12 | Must Have | Policy Director | In Progress
EP-06 | Financial Analytics | Strategic Analytics | 3 | 12 | Must Have | Dir of Finance | In Progress

## Feature Summary
Feature ID | Feature Name | Epic | Priority | Story Count | Related Dashboard | Status
FT-001 | Executive Dashboard | EP-01 | Must Have | 4 | Executive Dash | In Progress
FT-002 | Executive KPI Monitoring | EP-01 | Must Have | 4 | Executive Dash | In Progress
FT-005 | Executive Dashboard Filters | EP-01 | Must Have | 4 | Executive Dash | In Progress
FT-006 | Executive Dashboard Export | EP-01 | Should Have | 2 | Executive Dash | In Progress
FT-008 | Queue Performance Monitoring | EP-02 | Must Have | 4 | Operations Dash | In Progress
FT-009 | SLA Monitoring | EP-02 | Must Have | 4 | Operations Dash | In Progress
FT-010 | Productivity Analysis | EP-02 | Must Have | 4 | Operations Dash | In Progress
FT-012 | Operational Trend Analysis | EP-02 | Must Have | 4 | Operations Dash | In Progress
FT-015 | QA Dashboard | EP-03 | Must Have | 4 | Quality Dash | In Progress
FT-017 | Error Category Analysis | EP-03 | Must Have | 4 | Quality Dash | In Progress
FT-019 | QA Trend Analysis | EP-03 | Must Have | 4 | Quality Dash | In Progress
FT-021 | Staffing Overview | EP-04 | Must Have | 4 | Workforce Dash | In Progress
FT-022 | Occupancy Monitoring | EP-04 | Must Have | 4 | Workforce Dash | In Progress
FT-024 | Shrinkage Analysis | EP-04 | Must Have | 4 | Workforce Dash | In Progress
FT-027 | Appeals Dashboard | EP-05 | Must Have | 4 | Appeals Dash | In Progress
FT-028 | Appeals Intake | EP-05 | Must Have | 4 | Appeals Dash | In Progress
FT-031 | Overturn Rate Analysis | EP-05 | Must Have | 4 | Appeals Dash | In Progress
FT-033 | Revenue Dashboard | EP-06 | Must Have | 4 | Financial Dash | In Progress
FT-035 | Billing Attainment | EP-06 | Must Have | 4 | Financial Dash | In Progress
FT-038 | Margin Analysis | EP-06 | Must Have | 4 | Financial Dash | In Progress

## Sprint Planning
Sprint | Duration | Sprint Goal | Planned Stories | Story Points | Status
Sprint 1 | 2 Weeks | Data Modeling Foundation | 14 | 70 | Closed
Sprint 2 | 2 Weeks | Core DAX & Calculations | 14 | 42 | Active
Sprint 3 | 2 Weeks | Frontend Visuals | 14 | 70 | Planned
Sprint 4 | 2 Weeks | Security & UAT readiness | 14 | 28 | Planned

## Release Planning
Release | Release Objective | Included Epics | Included Features | Planned Sprint | Status
Release 1.0 | Core Dashboards for all domains | EP-01 to EP-06 | 14 Features | Sprint 4 | In Progress
Release 1.1 | Advanced Trends & Exporting | EP-01 to EP-06 | 6 Features | TBD | Planned
Release 2.0 | Predictive Analytics (Future) | TBD | TBD | TBD | Draft

## Backlog Metrics Dashboard
| Operations Analytics | 16 | Draft | 22 | Backlog | 22
Product Backlog Metrics Dashboard | Executive Analytics | 14 | Done | 14 | Sprint 1 | 14
| Quality Analytics | 12 | In Progress | 14 | Sprint 2 | 14
| Workforce Analytics | 12 | Ready for Development | 14 | Sprint 3 | 14
| Appeals Analytics | 12 | Ready for Refinement | 14 | Sprint 4 | 14
| Financial Analytics | 12