## 1_Master_RTM
Trace ID | Business Requirement ID | Business Requirement Summary | BRD Reference | Functional Requirement ID | FRD Reference | Epic ID | Epic Name | Feature ID | Feature Name | Product Backlog Story ID | User Story ID | User Story Title | Sprint | Release | Dashboard | KPI | Data Source | Acceptance Criteria Reference | UAT Test Case ID | UAT Status | Implementation Status | Business Owner | Product Owner | QA Owner | Remarks
RTM-001 | BRD-01-01 | Executive Visibility & Reporting | BRD-01 | FRD-01-01 | FRD-01 | EP-01 | Executive Analytics | FT-001 | Executive Dashboard | US-001 | US-001 | View Dashboard | Sprint 1 | Release 1.0 | Executive Landing | Total Volume, Global AHT | Data Warehouse DW_PROD | AC-001 | TC-001 | Not Started | In Progress | VP Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-002 | BRD-01-01 | Executive Visibility & Reporting | BRD-01 | FRD-01-01 | FRD-01 | EP-01 | Executive Analytics | FT-001 | Executive Dashboard | US-002 | US-002 | KPI Cards | Sprint 2 | Release 1.0 | Executive Header | Global AHT, Quality, Margin | Data Warehouse DW_PROD | AC-002 | TC-002 | Not Started | In Progress | VP Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-003 | BRD-01-01 | Executive Visibility & Reporting | BRD-01 | FRD-01-01 | FRD-01 | EP-01 | Executive Analytics | FT-005 | Executive Dashboard Filters | US-003 | US-003 | Dashboard Filters | Sprint 3 | Release 1.0 | Executive Filters | All | Data Warehouse DW_PROD | AC-003 | TC-003 | Not Started | Planned | VP Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-004 | BRD-01-01 | Executive Visibility & Reporting | BRD-01 | FRD-01-01 | FRD-01 | EP-01 | Executive Analytics | FT-002 | Executive KPI Monitoring | US-005 | US-005 | KPI Trend Analysis | Sprint 1 | Release 1.0 | Executive Trends | Quality Score (MoM) | Data Warehouse DW_PROD | AC-004 | TC-004 | Not Started | In Progress | VP Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-005 | BRD-01-01 | Executive Visibility & Reporting | BRD-01 | FRD-01-01 | FRD-01 | EP-01 | Executive Analytics | FT-002 | Executive KPI Monitoring | US-006 | US-006 | Performance Summary | Sprint 2 | Release 1.0 | Executive Summary | Volume, AHT, Quality | Data Warehouse DW_PROD | AC-005 | TC-005 | Not Started | In Progress | VP Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-006 | BRD-01-01 | Executive Visibility & Reporting | BRD-01 | FRD-01-01 | FRD-01 | EP-01 | Executive Analytics | FT-004 | Executive Drill-through | US-010 | US-010 | Drill to Operations | Sprint 3 | Release 1.0 | Cross-Navigation | N/A | Data Warehouse DW_PROD | AC-006 | TC-006 | Not Started | Planned | VP Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-007 | BRD-01-01 | Executive Visibility & Reporting | BRD-01 | FRD-01-01 | FRD-01 | EP-01 | Executive Analytics | FT-004 | Executive Drill-through | US-011 | US-011 | Drill to Workforce | Sprint 3 | Release 1.0 | Cross-Navigation | N/A | Data Warehouse DW_PROD | AC-007 | TC-007 | Not Started | Planned | VP Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-008 | BRD-01-01 | Executive Visibility & Reporting | BRD-01 | FRD-01-01 | FRD-01 | EP-01 | Executive Analytics | FT-006 | Executive Dashboard Export | US-013 | US-013 | Export Reports | Backlog | Release 1.0 | Executive Export | All | Data Warehouse DW_PROD | AC-008 | TC-008 | Not Started | Not Started | VP Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-009 | BRD-02-01 | Operations SLA & Queue Monitoring | BRD-02 | FRD-02-01 | FRD-02 | EP-02 | Operations Analytics | FT-008 | Queue Performance Monitoring | US-020 | US-020 | View Queue Performance | Sprint 1 | Release 1.0 | Ops Overview | Incoming, Handled Tickets | Data Warehouse DW_PROD | AC-009 | TC-009 | Not Started | In Progress | Dir Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-010 | BRD-02-01 | Operations SLA & Queue Monitoring | BRD-02 | FRD-02-01 | FRD-02 | EP-02 | Operations Analytics | FT-008 | Queue Performance Monitoring | US-021 | US-021 | Operations RLS | Sprint 4 | Release 1.0 | Global Ops Report | All | Data Warehouse DW_PROD | AC-010 | TC-010 | Not Started | Planned | Dir Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-011 | BRD-02-01 | Operations SLA & Queue Monitoring | BRD-02 | FRD-02-01 | FRD-02 | EP-02 | Operations Analytics | FT-008 | Queue Performance Monitoring | US-022 | US-022 | Operations Slicers | Sprint 3 | Release 1.0 | Ops Filters | All | Data Warehouse DW_PROD | AC-011 | TC-011 | Not Started | Planned | Dir Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-012 | BRD-02-01 | Operations SLA & Queue Monitoring | BRD-02 | FRD-02-01 | FRD-02 | EP-02 | Operations Analytics | FT-009 | SLA Monitoring | US-023 | US-023 | SLA Attainment DAX | Sprint 2 | Release 1.0 | Ops SLA | SLA Attainment % | Data Warehouse DW_PROD | AC-012 | TC-012 | Not Started | In Progress | Dir Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-013 | BRD-02-01 | Operations SLA & Queue Monitoring | BRD-02 | FRD-02-01 | FRD-02 | EP-02 | Operations Analytics | FT-009 | SLA Monitoring | US-024 | US-024 | SLA Breaches Alerts | Sprint 4 | Release 1.0 | PBI Alerts | Rolling SLA % | Data Warehouse DW_PROD | AC-013 | TC-013 | Not Started | Planned | Dir Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-014 | BRD-02-01 | Operations SLA & Queue Monitoring | BRD-02 | FRD-02-01 | FRD-02 | EP-02 | Operations Analytics | FT-010 | Productivity Analysis | US-025 | US-025 | Agent Productivity | Sprint 3 | Release 1.0 | Ops Productivity | AHT, Handled Count | Data Warehouse DW_PROD | AC-014 | TC-014 | Not Started | Planned | Dir Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-015 | BRD-02-01 | Operations SLA & Queue Monitoring | BRD-02 | FRD-02-01 | FRD-02 | EP-02 | Operations Analytics | FT-010 | Productivity Analysis | US-026 | US-026 | AHT Variance | Sprint 2 | Release 1.0 | Ops Productivity | AHT Variance | Data Warehouse DW_PROD | AC-015 | TC-015 | Not Started | In Progress | Dir Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-016 | BRD-02-01 | Operations SLA & Queue Monitoring | BRD-02 | FRD-02-01 | FRD-02 | EP-02 | Operations Analytics | FT-010 | Productivity Analysis | US-027 | US-027 | Agent Utilization | Sprint 3 | Release 1.0 | Ops Productivity | Utilization % | Data Warehouse DW_PROD | AC-016 | TC-016 | Not Started | Planned | Dir Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-017 | BRD-02-01 | Operations SLA & Queue Monitoring | BRD-02 | FRD-02-01 | FRD-02 | EP-02 | Operations Analytics | FT-011 | Backlog Analysis | US-028 | US-028 | Aging Ticket Backlog | Sprint 3 | Release 1.0 | Ops Backlog | Backlog Count | Data Warehouse DW_PROD | AC-017 | TC-017 | Not Started | Planned | Dir Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-018 | BRD-02-01 | Operations SLA & Queue Monitoring | BRD-02 | FRD-02-01 | FRD-02 | EP-02 | Operations Analytics | FT-012 | Operational Trend Analysis | US-029 | US-029 | Op Volume Trends | Backlog | Release 1.0 | Ops Trends | Incoming Volume | Data Warehouse DW_PROD | AC-018 | TC-018 | Not Started | Not Started | Dir Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-019 | BRD-02-01 | Operations SLA & Queue Monitoring | BRD-02 | FRD-02-01 | FRD-02 | EP-02 | Operations Analytics | FT-013 | Queue Drill-through | US-030 | US-030 | Queue Drill-through | Sprint 3 | Release 1.0 | Navigation | N/A | Data Warehouse DW_PROD | AC-019 | TC-019 | Not Started | Planned | Dir Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-020 | BRD-02-01 | Operations SLA & Queue Monitoring | BRD-02 | FRD-02-01 | FRD-02 | EP-02 | Operations Analytics | FT-014 | Operations Export | US-031 | US-031 | Export Ops Data | Backlog | Release 1.0 | Ops Export | All | Data Warehouse DW_PROD | AC-020 | TC-020 | Not Started | Not Started | Dir Operations | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-021 | BRD-03-01 | Quality Auditing & Fatal Error Tracking | BRD-03 | FRD-03-01 | FRD-03 | EP-03 | Quality Analytics | FT-015 | QA Dashboard | US-040 | US-040 | QA Data Modeling | Sprint 1 | Release 1.1 | QA Landing | Total Audits | Data Warehouse DW_PROD | AC-021 | TC-021 | Not Started | In Progress | QA Manager | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-022 | BRD-03-01 | Quality Auditing & Fatal Error Tracking | BRD-03 | FRD-03-01 | FRD-03 | EP-03 | Quality Analytics | FT-015 | QA Dashboard | US-041 | US-041 | QA RLS | Sprint 4 | Release 1.1 | Global QA Report | All | Data Warehouse DW_PROD | AC-022 | TC-022 | Not Started | Planned | QA Manager | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-023 | BRD-03-01 | Quality Auditing & Fatal Error Tracking | BRD-03 | FRD-03-01 | FRD-03 | EP-03 | Quality Analytics | FT-016 | Audit Performance | US-042 | US-042 | Audit Completion | Sprint 2 | Release 1.1 | QA Productivity | Audit Attainment % | Data Warehouse DW_PROD | AC-023 | TC-023 | Not Started | In Progress | QA Manager | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-024 | BRD-03-01 | Quality Auditing & Fatal Error Tracking | BRD-03 | FRD-03-01 | FRD-03 | EP-03 | Quality Analytics | FT-017 | Error Analysis | US-043 | US-043 | Fatal Error Logic | Sprint 2 | Release 1.1 | QA DAX | Fatal Error Rate % | Data Warehouse DW_PROD | AC-024 | TC-024 | Not Started | In Progress | QA Manager | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-025 | BRD-03-01 | Quality Auditing & Fatal Error Tracking | BRD-03 | FRD-03-01 | FRD-03 | EP-03 | Quality Analytics | FT-017 | Error Analysis | US-044 | US-044 | Error Pareto Chart | Sprint 3 | Release 1.1 | QA Breakdown | Error Count | Data Warehouse DW_PROD | AC-025 | TC-025 | Not Started | Planned | QA Manager | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-026 | BRD-03-01 | Quality Auditing & Fatal Error Tracking | BRD-03 | FRD-03-01 | FRD-03 | EP-03 | Quality Analytics | FT-018 | Coaching Effectiveness | US-045 | US-045 | Coaching Correlation | Sprint 3 | Release 1.1 | QA Coaching | Improvement % | Data Warehouse DW_PROD | AC-026 | TC-026 | Not Started | Planned | QA Manager | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-027 | BRD-03-01 | Quality Auditing & Fatal Error Tracking | BRD-03 | FRD-03-01 | FRD-03 | EP-03 | Quality Analytics | FT-019 | QA Trend Analysis | US-046 | US-046 | QA Trend Line | Sprint 3 | Release 1.1 | QA Trends | Quality Score | Data Warehouse DW_PROD | AC-027 | TC-027 | Not Started | Planned | QA Manager | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-028 | BRD-03-01 | Quality Auditing & Fatal Error Tracking | BRD-03 | FRD-03-01 | FRD-03 | EP-03 | Quality Analytics | FT-019 | QA Trend Analysis | US-047 | US-047 | Auditor Drill-down | Sprint 3 | Release 1.1 | QA Calibration | Average Score | Data Warehouse DW_PROD | AC-028 | TC-028 | Not Started | Planned | QA Manager | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-029 | BRD-03-01 | Quality Auditing & Fatal Error Tracking | BRD-03 | FRD-03-01 | FRD-03 | EP-03 | Quality Analytics | FT-020 | Quality Export | US-048 | US-048 | Export QA Logs | Backlog | Release 1.1 | QA Export | N/A | Data Warehouse DW_PROD | AC-029 | TC-029 | Not Started | Not Started | QA Manager | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-030 | BRD-04-01 | Workforce & Headcount Optimization | BRD-04 | FRD-04-01 | FRD-04 | EP-04 | Workforce Analytics | FT-021 | Staffing Overview | US-050 | US-050 | WFM Data Modeling | Sprint 1 | Release 1.1 | WFM Landing | Scheduled Hours | Data Warehouse DW_PROD | AC-030 | TC-030 | Not Started | In Progress | WFM Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-031 | BRD-04-01 | Workforce & Headcount Optimization | BRD-04 | FRD-04-01 | FRD-04 | EP-04 | Workforce Analytics | FT-021 | Staffing Overview | US-051 | US-051 | Real-time Coverage | Sprint 2 | Release 1.1 | WFM Coverage | Headcount Variance | Data Warehouse DW_PROD | AC-031 | TC-031 | Not Started | In Progress | WFM Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-032 | BRD-04-01 | Workforce & Headcount Optimization | BRD-04 | FRD-04-01 | FRD-04 | EP-04 | Workforce Analytics | FT-022 | Occupancy Monitoring | US-052 | US-052 | Occupancy Gauge | Sprint 2 | Release 1.1 | WFM Occupancy | Occupancy % | Data Warehouse DW_PROD | AC-032 | TC-032 | Not Started | In Progress | WFM Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-033 | BRD-04-01 | Workforce & Headcount Optimization | BRD-04 | FRD-04-01 | FRD-04 | EP-04 | Workforce Analytics | FT-023 | Schedule Adherence | US-053 | US-053 | Schedule Adherence | Sprint 3 | Release 1.1 | WFM Adherence | Adherence % | Data Warehouse DW_PROD | AC-033 | TC-033 | Not Started | Planned | WFM Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-034 | BRD-04-01 | Workforce & Headcount Optimization | BRD-04 | FRD-04-01 | FRD-04 | EP-04 | Workforce Analytics | FT-024 | Shrinkage Analysis | US-054 | US-054 | Shrinkage Breakdown | Sprint 3 | Release 1.1 | WFM Shrinkage | Shrinkage % | Data Warehouse DW_PROD | AC-034 | TC-034 | Not Started | Planned | WFM Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-035 | BRD-04-01 | Workforce & Headcount Optimization | BRD-04 | FRD-04-01 | FRD-04 | EP-04 | Workforce Analytics | FT-024 | Shrinkage Analysis | US-055 | US-055 | Shrinkage Alerts | Sprint 4 | Release 1.1 | PBI Alerts | Unplanned Shrinkage | Data Warehouse DW_PROD | AC-035 | TC-035 | Not Started | Planned | WFM Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-036 | BRD-04-01 | Workforce & Headcount Optimization | BRD-04 | FRD-04-01 | FRD-04 | EP-04 | Workforce Analytics | FT-025 | Workforce Trends | US-056 | US-056 | Absenteeism Trends | Backlog | Release 1.1 | WFM Trends | Absenteeism % | Data Warehouse DW_PROD | AC-036 | TC-036 | Not Started | Not Started | WFM Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-037 | BRD-04-01 | Workforce & Headcount Optimization | BRD-04 | FRD-04-01 | FRD-04 | EP-04 | Workforce Analytics | FT-026 | Workforce Export | US-057 | US-057 | Export WFM Data | Backlog | Release 1.1 | WFM Export | Actual Hours | Data Warehouse DW_PROD | AC-037 | TC-037 | Not Started | Not Started | WFM Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-038 | BRD-05-01 | Appeals & Overturn Rate Management | BRD-05 | FRD-05-01 | FRD-05 | EP-05 | Appeals Analytics | FT-027 | Appeals Dashboard | US-060 | US-060 | Appeals Data Modeling | Sprint 1 | Release 1.1 | Appeals Landing | Total Appeals | Data Warehouse DW_PROD | AC-038 | TC-038 | Not Started | In Progress | Policy Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-039 | BRD-05-01 | Appeals & Overturn Rate Management | BRD-05 | FRD-05-01 | FRD-05 | EP-05 | Appeals Analytics | FT-027 | Appeals Dashboard | US-061 | US-061 | Appeals RLS | Sprint 4 | Release 1.1 | Global Appeals Report | All | Data Warehouse DW_PROD | AC-039 | TC-039 | Not Started | Planned | Policy Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-040 | BRD-05-01 | Appeals & Overturn Rate Management | BRD-05 | FRD-05-01 | FRD-05 | EP-05 | Appeals Analytics | FT-028 | Appeals Intake | US-062 | US-062 | Appeals Intake | Sprint 2 | Release 1.1 | Appeals Intake | Incoming Appeals | Data Warehouse DW_PROD | AC-040 | TC-040 | Not Started | In Progress | Policy Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-041 | BRD-05-01 | Appeals & Overturn Rate Management | BRD-05 | FRD-05-01 | FRD-05 | EP-05 | Appeals Analytics | FT-029 | Appeals Resolution | US-063 | US-063 | Appeals TAT | Sprint 2 | Release 1.1 | Appeals Resolution | Appeals Avg TAT | Data Warehouse DW_PROD | AC-041 | TC-041 | Not Started | In Progress | Policy Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-042 | BRD-05-01 | Appeals & Overturn Rate Management | BRD-05 | FRD-05-01 | FRD-05 | EP-05 | Appeals Analytics | FT-029 | Appeals Resolution | US-064 | US-064 | Disposition Pie | Sprint 3 | Release 1.1 | Appeals Resolution | Disposition Volumes | Data Warehouse DW_PROD | AC-042 | TC-042 | Not Started | Planned | Policy Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-043 | BRD-05-01 | Appeals & Overturn Rate Management | BRD-05 | FRD-05-01 | FRD-05 | EP-05 | Appeals Analytics | FT-030 | Appeal Backlog | US-065 | US-065 | Aging Backlog | Sprint 3 | Release 1.1 | Appeals Backlog | Open Appeals | Data Warehouse DW_PROD | AC-043 | TC-043 | Not Started | Planned | Policy Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-044 | BRD-05-01 | Appeals & Overturn Rate Management | BRD-05 | FRD-05-01 | FRD-05 | EP-05 | Appeals Analytics | FT-031 | Overturn Analysis | US-066 | US-066 | Overturn Rate | Sprint 3 | Release 1.1 | Appeals Overturn | Overturn Rate % | Data Warehouse DW_PROD | AC-044 | TC-044 | Not Started | Planned | Policy Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-045 | BRD-05-01 | Appeals & Overturn Rate Management | BRD-05 | FRD-05-01 | FRD-05 | EP-05 | Appeals Analytics | FT-032 | Appeals Export | US-067 | US-067 | Export Appeals | Backlog | Release 1.1 | Appeals Export | N/A | Data Warehouse DW_PROD | AC-045 | TC-045 | Not Started | Not Started | Policy Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-046 | BRD-06-01 | Financial Margins & Billing Validation | BRD-06 | FRD-06-01 | FRD-06 | EP-06 | Financial Analytics | FT-033 | Financial Dashboard | US-070 | US-070 | Financial Data Integration | Sprint 1 | Release 2.0 | Finance Landing | Gross Revenue | Data Warehouse DW_PROD | AC-046 | TC-046 | Not Started | In Progress | Finance Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-047 | BRD-06-01 | Financial Margins & Billing Validation | BRD-06 | FRD-06-01 | FRD-06 | EP-06 | Financial Analytics | FT-033 | Financial Dashboard | US-071 | US-071 | Financial RLS | Sprint 4 | Release 2.0 | Global Finance Report | All | Data Warehouse DW_PROD | AC-047 | TC-047 | Not Started | Planned | Finance Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-048 | BRD-06-01 | Financial Margins & Billing Validation | BRD-06 | FRD-06-01 | FRD-06 | EP-06 | Financial Analytics | FT-034 | Revenue Tracking | US-072 | US-072 | Billable vs Non-Billable | Sprint 2 | Release 2.0 | Finance Revenue | Billable Utilization | Data Warehouse DW_PROD | AC-048 | TC-048 | Not Started | In Progress | Finance Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-049 | BRD-06-01 | Financial Margins & Billing Validation | BRD-06 | FRD-06-01 | FRD-06 | EP-06 | Financial Analytics | FT-035 | Margin Analysis | US-073 | US-073 | Gross Margin DAX | Sprint 2 | Release 2.0 | Finance Margin | Gross Margin % | Data Warehouse DW_PROD | AC-049 | TC-049 | Not Started | In Progress | Finance Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-050 | BRD-06-01 | Financial Margins & Billing Validation | BRD-06 | FRD-06-01 | FRD-06 | EP-06 | Financial Analytics | FT-035 | Margin Analysis | US-074 | US-074 | Margin Trend | Sprint 3 | Release 2.0 | Finance Margin | Gross Margin % | Data Warehouse DW_PROD | AC-050 | TC-050 | Not Started | Planned | Finance Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-051 | BRD-06-01 | Financial Margins & Billing Validation | BRD-06 | FRD-06-01 | FRD-06 | EP-06 | Financial Analytics | FT-036 | CPT Tracking | US-075 | US-075 | Cost Per Ticket | Sprint 2 | Release 2.0 | Finance Cost | Cost Per Ticket | Data Warehouse DW_PROD | AC-051 | TC-051 | Not Started | In Progress | Finance Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-052 | BRD-06-01 | Financial Margins & Billing Validation | BRD-06 | FRD-06-01 | FRD-06 | EP-06 | Financial Analytics | FT-037 | SLA Penalties | US-076 | US-076 | SLA Penalty | Sprint 3 | Release 2.0 | Finance Penalties | Penalty Deductions | Data Warehouse DW_PROD | AC-052 | TC-052 | Not Started | Planned | Finance Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-053 | BRD-06-01 | Financial Margins & Billing Validation | BRD-06 | FRD-06-01 | FRD-06 | EP-06 | Financial Analytics | FT-038 | Billing Recon | US-077 | US-077 | Billing Reconciliation | Sprint 3 | Release 2.0 | Finance Recon | Unbilled Variance | Data Warehouse DW_PROD | AC-053 | TC-053 | Not Started | Planned | Finance Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-054 | BRD-06-01 | Financial Margins & Billing Validation | BRD-06 | FRD-06-01 | FRD-06 | EP-06 | Financial Analytics | FT-039 | Financial Forecasting | US-078 | US-078 | Revenue Forecasting | Backlog | Release 2.0 | Finance Forecast | Projected Revenue | Data Warehouse DW_PROD | AC-054 | TC-054 | Not Started | Not Started | Finance Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.
RTM-055 | BRD-06-01 | Financial Margins & Billing Validation | BRD-06 | FRD-06-01 | FRD-06 | EP-06 | Financial Analytics | FT-040 | Financial Export | US-079 | US-079 | Export Invoices | Backlog | Release 2.0 | Finance Export | N/A | Data Warehouse DW_PROD | AC-055 | TC-055 | Not Started | Not Started | Finance Director | PO Team | QA Automation Team | Mapped directly from US-04 detailed stories.

## 2_BRD_to_FRD
BR ID | Business Requirement | Related FR ID | Functional Requirement | Coverage Status
BRD-01-01 | Executive Visibility & Reporting | FRD-01-01 | FRD-01 | Fully Covered
BRD-02-01 | Operations SLA & Queue Monitoring | FRD-02-01 | FRD-02 | Fully Covered
BRD-03-01 | Quality Auditing & Fatal Error Tracking | FRD-03-01 | FRD-03 | Fully Covered
BRD-04-01 | Workforce & Headcount Optimization | FRD-04-01 | FRD-04 | Fully Covered
BRD-05-01 | Appeals & Overturn Rate Management | FRD-05-01 | FRD-05 | Fully Covered
BRD-06-01 | Financial Margins & Billing Validation | FRD-06-01 | FRD-06 | Fully Covered

## 3_FRD_to_Agile
FR ID | Functional Requirement | Epic | Feature | User Story | Sprint
FRD-01-01 | FRD-01 | EP-01 | FT-001 | US-001 | Sprint 1
FRD-01-01 | FRD-01 | EP-01 | FT-001 | US-002 | Sprint 2
FRD-01-01 | FRD-01 | EP-01 | FT-005 | US-003 | Sprint 3
FRD-01-01 | FRD-01 | EP-01 | FT-002 | US-005 | Sprint 1
FRD-01-01 | FRD-01 | EP-01 | FT-002 | US-006 | Sprint 2
FRD-01-01 | FRD-01 | EP-01 | FT-004 | US-010 | Sprint 3
FRD-01-01 | FRD-01 | EP-01 | FT-004 | US-011 | Sprint 3
FRD-01-01 | FRD-01 | EP-01 | FT-006 | US-013 | Backlog
FRD-02-01 | FRD-02 | EP-02 | FT-008 | US-020 | Sprint 1
FRD-02-01 | FRD-02 | EP-02 | FT-008 | US-021 | Sprint 4
FRD-02-01 | FRD-02 | EP-02 | FT-008 | US-022 | Sprint 3
FRD-02-01 | FRD-02 | EP-02 | FT-009 | US-023 | Sprint 2
FRD-02-01 | FRD-02 | EP-02 | FT-009 | US-024 | Sprint 4
FRD-02-01 | FRD-02 | EP-02 | FT-010 | US-025 | Sprint 3
FRD-02-01 | FRD-02 | EP-02 | FT-010 | US-026 | Sprint 2
FRD-02-01 | FRD-02 | EP-02 | FT-010 | US-027 | Sprint 3
FRD-02-01 | FRD-02 | EP-02 | FT-011 | US-028 | Sprint 3
FRD-02-01 | FRD-02 | EP-02 | FT-012 | US-029 | Backlog
FRD-02-01 | FRD-02 | EP-02 | FT-013 | US-030 | Sprint 3
FRD-02-01 | FRD-02 | EP-02 | FT-014 | US-031 | Backlog
FRD-03-01 | FRD-03 | EP-03 | FT-015 | US-040 | Sprint 1
FRD-03-01 | FRD-03 | EP-03 | FT-015 | US-041 | Sprint 4
FRD-03-01 | FRD-03 | EP-03 | FT-016 | US-042 | Sprint 2
FRD-03-01 | FRD-03 | EP-03 | FT-017 | US-043 | Sprint 2
FRD-03-01 | FRD-03 | EP-03 | FT-017 | US-044 | Sprint 3
FRD-03-01 | FRD-03 | EP-03 | FT-018 | US-045 | Sprint 3
FRD-03-01 | FRD-03 | EP-03 | FT-019 | US-046 | Sprint 3
FRD-03-01 | FRD-03 | EP-03 | FT-019 | US-047 | Sprint 3
FRD-03-01 | FRD-03 | EP-03 | FT-020 | US-048 | Backlog
FRD-04-01 | FRD-04 | EP-04 | FT-021 | US-050 | Sprint 1
FRD-04-01 | FRD-04 | EP-04 | FT-021 | US-051 | Sprint 2
FRD-04-01 | FRD-04 | EP-04 | FT-022 | US-052 | Sprint 2
FRD-04-01 | FRD-04 | EP-04 | FT-023 | US-053 | Sprint 3
FRD-04-01 | FRD-04 | EP-04 | FT-024 | US-054 | Sprint 3
FRD-04-01 | FRD-04 | EP-04 | FT-024 | US-055 | Sprint 4
FRD-04-01 | FRD-04 | EP-04 | FT-025 | US-056 | Backlog
FRD-04-01 | FRD-04 | EP-04 | FT-026 | US-057 | Backlog
FRD-05-01 | FRD-05 | EP-05 | FT-027 | US-060 | Sprint 1
FRD-05-01 | FRD-05 | EP-05 | FT-027 | US-061 | Sprint 4
FRD-05-01 | FRD-05 | EP-05 | FT-028 | US-062 | Sprint 2
FRD-05-01 | FRD-05 | EP-05 | FT-029 | US-063 | Sprint 2
FRD-05-01 | FRD-05 | EP-05 | FT-029 | US-064 | Sprint 3
FRD-05-01 | FRD-05 | EP-05 | FT-030 | US-065 | Sprint 3
FRD-05-01 | FRD-05 | EP-05 | FT-031 | US-066 | Sprint 3
FRD-05-01 | FRD-05 | EP-05 | FT-032 | US-067 | Backlog
FRD-06-01 | FRD-06 | EP-06 | FT-033 | US-070 | Sprint 1
FRD-06-01 | FRD-06 | EP-06 | FT-033 | US-071 | Sprint 4
FRD-06-01 | FRD-06 | EP-06 | FT-034 | US-072 | Sprint 2
FRD-06-01 | FRD-06 | EP-06 | FT-035 | US-073 | Sprint 2
FRD-06-01 | FRD-06 | EP-06 | FT-035 | US-074 | Sprint 3
FRD-06-01 | FRD-06 | EP-06 | FT-036 | US-075 | Sprint 2
FRD-06-01 | FRD-06 | EP-06 | FT-037 | US-076 | Sprint 3
FRD-06-01 | FRD-06 | EP-06 | FT-038 | US-077 | Sprint 3
FRD-06-01 | FRD-06 | EP-06 | FT-039 | US-078 | Backlog
FRD-06-01 | FRD-06 | EP-06 | FT-040 | US-079 | Backlog

## 4_Dash_KPI_Trace
Dashboard | KPI | Related User Story | Related Feature | Related FR | Related BR
Executive Landing | Total Volume, Global AHT | US-001 | FT-001 | FRD-01-01 | BRD-01-01
Executive Header | Global AHT, Quality, Margin | US-002 | FT-001 | FRD-01-01 | BRD-01-01
Executive Filters | All | US-003 | FT-005 | FRD-01-01 | BRD-01-01
Executive Trends | Quality Score (MoM) | US-005 | FT-002 | FRD-01-01 | BRD-01-01
Executive Summary | Volume, AHT, Quality | US-006 | FT-002 | FRD-01-01 | BRD-01-01
Cross-Navigation | N/A | US-010 | FT-004 | FRD-01-01 | BRD-01-01
Cross-Navigation | N/A | US-011 | FT-004 | FRD-01-01 | BRD-01-01
Executive Export | All | US-013 | FT-006 | FRD-01-01 | BRD-01-01
Ops Overview | Incoming, Handled Tickets | US-020 | FT-008 | FRD-02-01 | BRD-02-01
Global Ops Report | All | US-021 | FT-008 | FRD-02-01 | BRD-02-01
Ops Filters | All | US-022 | FT-008 | FRD-02-01 | BRD-02-01
Ops SLA | SLA Attainment % | US-023 | FT-009 | FRD-02-01 | BRD-02-01
PBI Alerts | Rolling SLA % | US-024 | FT-009 | FRD-02-01 | BRD-02-01
Ops Productivity | AHT, Handled Count | US-025 | FT-010 | FRD-02-01 | BRD-02-01
Ops Productivity | AHT Variance | US-026 | FT-010 | FRD-02-01 | BRD-02-01
Ops Productivity | Utilization % | US-027 | FT-010 | FRD-02-01 | BRD-02-01
Ops Backlog | Backlog Count | US-028 | FT-011 | FRD-02-01 | BRD-02-01
Ops Trends | Incoming Volume | US-029 | FT-012 | FRD-02-01 | BRD-02-01
Navigation | N/A | US-030 | FT-013 | FRD-02-01 | BRD-02-01
Ops Export | All | US-031 | FT-014 | FRD-02-01 | BRD-02-01
QA Landing | Total Audits | US-040 | FT-015 | FRD-03-01 | BRD-03-01
Global QA Report | All | US-041 | FT-015 | FRD-03-01 | BRD-03-01
QA Productivity | Audit Attainment % | US-042 | FT-016 | FRD-03-01 | BRD-03-01
QA DAX | Fatal Error Rate % | US-043 | FT-017 | FRD-03-01 | BRD-03-01
QA Breakdown | Error Count | US-044 | FT-017 | FRD-03-01 | BRD-03-01
QA Coaching | Improvement % | US-045 | FT-018 | FRD-03-01 | BRD-03-01
QA Trends | Quality Score | US-046 | FT-019 | FRD-03-01 | BRD-03-01
QA Calibration | Average Score | US-047 | FT-019 | FRD-03-01 | BRD-03-01
QA Export | N/A | US-048 | FT-020 | FRD-03-01 | BRD-03-01
WFM Landing | Scheduled Hours | US-050 | FT-021 | FRD-04-01 | BRD-04-01
WFM Coverage | Headcount Variance | US-051 | FT-021 | FRD-04-01 | BRD-04-01
WFM Occupancy | Occupancy % | US-052 | FT-022 | FRD-04-01 | BRD-04-01
WFM Adherence | Adherence % | US-053 | FT-023 | FRD-04-01 | BRD-04-01
WFM Shrinkage | Shrinkage % | US-054 | FT-024 | FRD-04-01 | BRD-04-01
PBI Alerts | Unplanned Shrinkage | US-055 | FT-024 | FRD-04-01 | BRD-04-01
WFM Trends | Absenteeism % | US-056 | FT-025 | FRD-04-01 | BRD-04-01
WFM Export | Actual Hours | US-057 | FT-026 | FRD-04-01 | BRD-04-01
Appeals Landing | Total Appeals | US-060 | FT-027 | FRD-05-01 | BRD-05-01
Global Appeals Report | All | US-061 | FT-027 | FRD-05-01 | BRD-05-01
Appeals Intake | Incoming Appeals | US-062 | FT-028 | FRD-05-01 | BRD-05-01
Appeals Resolution | Appeals Avg TAT | US-063 | FT-029 | FRD-05-01 | BRD-05-01
Appeals Resolution | Disposition Volumes | US-064 | FT-029 | FRD-05-01 | BRD-05-01
Appeals Backlog | Open Appeals | US-065 | FT-030 | FRD-05-01 | BRD-05-01
Appeals Overturn | Overturn Rate % | US-066 | FT-031 | FRD-05-01 | BRD-05-01
Appeals Export | N/A | US-067 | FT-032 | FRD-05-01 | BRD-05-01
Finance Landing | Gross Revenue | US-070 | FT-033 | FRD-06-01 | BRD-06-01
Global Finance Report | All | US-071 | FT-033 | FRD-06-01 | BRD-06-01
Finance Revenue | Billable Utilization | US-072 | FT-034 | FRD-06-01 | BRD-06-01
Finance Margin | Gross Margin % | US-073 | FT-035 | FRD-06-01 | BRD-06-01
Finance Margin | Gross Margin % | US-074 | FT-035 | FRD-06-01 | BRD-06-01
Finance Cost | Cost Per Ticket | US-075 | FT-036 | FRD-06-01 | BRD-06-01
Finance Penalties | Penalty Deductions | US-076 | FT-037 | FRD-06-01 | BRD-06-01
Finance Recon | Unbilled Variance | US-077 | FT-038 | FRD-06-01 | BRD-06-01
Finance Forecast | Projected Revenue | US-078 | FT-039 | FRD-06-01 | BRD-06-01
Finance Export | N/A | US-079 | FT-040 | FRD-06-01 | BRD-06-01

## 5_UAT_Traceability
User Story | Acceptance Criteria | UAT Test Case | Expected Result | Actual Result | Status
US-001 | AC-001 | TC-001 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-002 | AC-002 | TC-002 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-003 | AC-003 | TC-003 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-005 | AC-004 | TC-004 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-006 | AC-005 | TC-005 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-010 | AC-006 | TC-006 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-011 | AC-007 | TC-007 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-013 | AC-008 | TC-008 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-020 | AC-009 | TC-009 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-021 | AC-010 | TC-010 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-022 | AC-011 | TC-011 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-023 | AC-012 | TC-012 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-024 | AC-013 | TC-013 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-025 | AC-014 | TC-014 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-026 | AC-015 | TC-015 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-027 | AC-016 | TC-016 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-028 | AC-017 | TC-017 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-029 | AC-018 | TC-018 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-030 | AC-019 | TC-019 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-031 | AC-020 | TC-020 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-040 | AC-021 | TC-021 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-041 | AC-022 | TC-022 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-042 | AC-023 | TC-023 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-043 | AC-024 | TC-024 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-044 | AC-025 | TC-025 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-045 | AC-026 | TC-026 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-046 | AC-027 | TC-027 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-047 | AC-028 | TC-028 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-048 | AC-029 | TC-029 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-050 | AC-030 | TC-030 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-051 | AC-031 | TC-031 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-052 | AC-032 | TC-032 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-053 | AC-033 | TC-033 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-054 | AC-034 | TC-034 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-055 | AC-035 | TC-035 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-056 | AC-036 | TC-036 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-057 | AC-037 | TC-037 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-060 | AC-038 | TC-038 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-061 | AC-039 | TC-039 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-062 | AC-040 | TC-040 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-063 | AC-041 | TC-041 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-064 | AC-042 | TC-042 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-065 | AC-043 | TC-043 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-066 | AC-044 | TC-044 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-067 | AC-045 | TC-045 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-070 | AC-046 | TC-046 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-071 | AC-047 | TC-047 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-072 | AC-048 | TC-048 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-073 | AC-049 | TC-049 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-074 | AC-050 | TC-050 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-075 | AC-051 | TC-051 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-076 | AC-052 | TC-052 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-077 | AC-053 | TC-053 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-078 | AC-054 | TC-054 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started
US-079 | AC-055 | TC-055 | Dashboard loads and calculates KPIs accurately per Acceptance Criteria. | To Be Executed | Not Started

## 6_Summary_Dashboard
Requirement Traceability Summary Dashboard
Enterprise Trust & Safety Operations Analytics Data Warehouse
Stories by Epic
Operations Analytics | 12
Financial Analytics | 10
Quality Analytics | 9
Executive Analytics | 8
Workforce Analytics | 8
Appeals Analytics | 8
Stories by Sprint
Sprint 3 | 20
Sprint 2 | 13
Backlog | 9
Sprint 1 | 7
Sprint 4 | 6
Stories by Status
Planned | 26
In Progress | 20
Not Started | 9