## 1_UAT_Overview
UAT Overview & Guidelines
Project Information
Project Name | Enterprise Trust & Safety Operations Analytics Data Warehouse
UAT Document Name | UAT-01: User Acceptance Testing (UAT) Workbook
Version | 1.0
Status | Final - Ready for Execution
Prepared By | Business Analyst
Reviewed By | QA Lead, Product Owner
Approved By | Business Sponsor
Planned UAT Dates | TBD (Post-Sprint 4)
Environment | UAT / Pre-Prod Power BI Workspace
Build Version | Release 1.0 (MVP) through Release 2.0
Purpose
Purpose of UAT | To validate that the deployed dashboards and data models meet the business requirements and are fit for operational use.
QA vs UAT | QA focuses on technical correctness and bug finding. UAT focuses on business process validation and end-user acceptance.
Ownership | UAT is strictly owned and executed by the designated Business Stakeholders/Users, guided by the Product Owner.
Scope
In Scope | Dashboard validation, KPI accuracy, Filters, Drill-through, Exports, Role-Level Security (RLS).
Out of Scope | Unit testing, System Integration Testing, Load/Performance testing, Security vulnerability testing.
Entry Criteria
1. Development Completed 2. QA Passed & Signed-off 3. RTM Updated 4. UAT Test Environment Provisioned & Data Refreshed
Exit Criteria
1. All Critical and High Test Cases Passed 2. No High Severity Defects Open 3. Formal Business Sign-off Received
Roles & Responsibilities
Business Analyst | Maintains UAT documentation, tracks defects, acts as liaison between IT and Business.
Product Owner | Approves UAT test scope, prioritizes defect resolution.
Business Users | Execute test cases, document Actual Results, log defects, provide final approval.
QA Team | Provides test data, ensures environment stability.
Developers | Fix UAT defects, deploy hotfixes to UAT environment.
Project Manager | Tracks UAT schedule, coordinates sign-offs.

## 2_UAT_Test_Case_Register
Test Case ID | RTM ID | User Story ID | User Story Title | Requirement ID | Epic | Feature | Dashboard | KPI | Test Scenario | Test Steps | Test Data | Expected Result | Actual Result | Tester | Test Date | Status | Severity | Remarks
UAT-001 | RTM-001 | US-001 | View Dashboard | BRD-01-01 | EP-01 | FT-001 | Executive Landing | Total Volume, Global AHT | Validate View Dashboard functionality | 1. Navigate to Executive Landing 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'View Dashboard' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-002 | RTM-002 | US-002 | KPI Cards | BRD-01-01 | EP-01 | FT-001 | Executive Header | Global AHT, Quality, Margin | Validate KPI Cards functionality | 1. Navigate to Executive Header 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'KPI Cards' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-003 | RTM-003 | US-003 | Dashboard Filters | BRD-01-01 | EP-01 | FT-005 | Executive Filters | All | Validate Dashboard Filters functionality | 1. Navigate to Executive Filters 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Dashboard Filters' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-004 | RTM-004 | US-005 | KPI Trend Analysis | BRD-01-01 | EP-01 | FT-002 | Executive Trends | Quality Score (MoM) | Validate KPI Trend Analysis functionality | 1. Navigate to Executive Trends 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'KPI Trend Analysis' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-005 | RTM-005 | US-006 | Performance Summary | BRD-01-01 | EP-01 | FT-002 | Executive Summary | Volume, AHT, Quality | Validate Performance Summary functionality | 1. Navigate to Executive Summary 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Performance Summary' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-006 | RTM-006 | US-010 | Drill to Operations | BRD-01-01 | EP-01 | FT-004 | Cross-Navigation | N/A | Validate Drill-through from Executive Analytics | 1. Right-click data point 2. Select drill-through 3. Verify target page inherits filters. | Mock Production Data (Sprint 4) | System successfully completes 'Drill to Operations' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-007 | RTM-007 | US-011 | Drill to Workforce | BRD-01-01 | EP-01 | FT-004 | Cross-Navigation | N/A | Validate Drill-through from Executive Analytics | 1. Right-click data point 2. Select drill-through 3. Verify target page inherits filters. | Mock Production Data (Sprint 4) | System successfully completes 'Drill to Workforce' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-008 | RTM-008 | US-013 | Export Reports | BRD-01-01 | EP-01 | FT-006 | Executive Export | All | Validate export feature for Executive Export | 1. Apply filters 2. Click Export 3. Verify downloaded file contents match visuals. | Mock Production Data (Sprint 4) | System successfully completes 'Export Reports' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-009 | RTM-009 | US-020 | View Queue Performance | BRD-02-01 | EP-02 | FT-008 | Ops Overview | Incoming, Handled Tickets | Validate View Queue Performance functionality | 1. Navigate to Ops Overview 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'View Queue Performance' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-010 | RTM-010 | US-021 | Operations RLS | BRD-02-01 | EP-02 | FT-008 | Global Ops Report | All | Validate Role-Level Security for Operations Analytics | 1. Log in as restricted user 2. Navigate to report 3. Ensure unauthorized data is hidden. | Mock Production Data (Sprint 4) | System successfully completes 'Operations RLS' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | High | Mapped to RTM-01.
UAT-011 | RTM-011 | US-022 | Operations Slicers | BRD-02-01 | EP-02 | FT-008 | Ops Filters | All | Validate Operations Slicers functionality | 1. Navigate to Ops Filters 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Operations Slicers' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-012 | RTM-012 | US-023 | SLA Attainment DAX | BRD-02-01 | EP-02 | FT-009 | Ops SLA | SLA Attainment % | Validate SLA Attainment DAX functionality | 1. Navigate to Ops SLA 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'SLA Attainment DAX' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-013 | RTM-013 | US-024 | SLA Breaches Alerts | BRD-02-01 | EP-02 | FT-009 | PBI Alerts | Rolling SLA % | Validate SLA Breaches Alerts functionality | 1. Navigate to PBI Alerts 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'SLA Breaches Alerts' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-014 | RTM-014 | US-025 | Agent Productivity | BRD-02-01 | EP-02 | FT-010 | Ops Productivity | AHT, Handled Count | Validate Agent Productivity functionality | 1. Navigate to Ops Productivity 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Agent Productivity' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-015 | RTM-015 | US-026 | AHT Variance | BRD-02-01 | EP-02 | FT-010 | Ops Productivity | AHT Variance | Validate AHT Variance functionality | 1. Navigate to Ops Productivity 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'AHT Variance' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-016 | RTM-016 | US-027 | Agent Utilization | BRD-02-01 | EP-02 | FT-010 | Ops Productivity | Utilization % | Validate Agent Utilization functionality | 1. Navigate to Ops Productivity 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Agent Utilization' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-017 | RTM-017 | US-028 | Aging Ticket Backlog | BRD-02-01 | EP-02 | FT-011 | Ops Backlog | Backlog Count | Validate Aging Ticket Backlog functionality | 1. Navigate to Ops Backlog 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Aging Ticket Backlog' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-018 | RTM-018 | US-029 | Op Volume Trends | BRD-02-01 | EP-02 | FT-012 | Ops Trends | Incoming Volume | Validate Op Volume Trends functionality | 1. Navigate to Ops Trends 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Op Volume Trends' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-019 | RTM-019 | US-030 | Queue Drill-through | BRD-02-01 | EP-02 | FT-013 | Navigation | N/A | Validate Drill-through from Operations Analytics | 1. Right-click data point 2. Select drill-through 3. Verify target page inherits filters. | Mock Production Data (Sprint 4) | System successfully completes 'Queue Drill-through' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-020 | RTM-020 | US-031 | Export Ops Data | BRD-02-01 | EP-02 | FT-014 | Ops Export | All | Validate export feature for Ops Export | 1. Apply filters 2. Click Export 3. Verify downloaded file contents match visuals. | Mock Production Data (Sprint 4) | System successfully completes 'Export Ops Data' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | High | Mapped to RTM-01.
UAT-021 | RTM-021 | US-040 | QA Data Modeling | BRD-03-01 | EP-03 | FT-015 | QA Landing | Total Audits | Validate QA Data Modeling functionality | 1. Navigate to QA Landing 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'QA Data Modeling' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | High | Mapped to RTM-01.
UAT-022 | RTM-022 | US-041 | QA RLS | BRD-03-01 | EP-03 | FT-015 | Global QA Report | All | Validate Role-Level Security for Quality Analytics | 1. Log in as restricted user 2. Navigate to report 3. Ensure unauthorized data is hidden. | Mock Production Data (Sprint 4) | System successfully completes 'QA RLS' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | High | Mapped to RTM-01.
UAT-023 | RTM-023 | US-042 | Audit Completion | BRD-03-01 | EP-03 | FT-016 | QA Productivity | Audit Attainment % | Validate Audit Completion functionality | 1. Navigate to QA Productivity 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Audit Completion' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-024 | RTM-024 | US-043 | Fatal Error Logic | BRD-03-01 | EP-03 | FT-017 | QA DAX | Fatal Error Rate % | Validate Fatal Error Logic functionality | 1. Navigate to QA DAX 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Fatal Error Logic' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-025 | RTM-025 | US-044 | Error Pareto Chart | BRD-03-01 | EP-03 | FT-017 | QA Breakdown | Error Count | Validate Error Pareto Chart functionality | 1. Navigate to QA Breakdown 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Error Pareto Chart' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-026 | RTM-026 | US-045 | Coaching Correlation | BRD-03-01 | EP-03 | FT-018 | QA Coaching | Improvement % | Validate Coaching Correlation functionality | 1. Navigate to QA Coaching 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Coaching Correlation' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-027 | RTM-027 | US-046 | QA Trend Line | BRD-03-01 | EP-03 | FT-019 | QA Trends | Quality Score | Validate QA Trend Line functionality | 1. Navigate to QA Trends 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'QA Trend Line' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-028 | RTM-028 | US-047 | Auditor Drill-down | BRD-03-01 | EP-03 | FT-019 | QA Calibration | Average Score | Validate Drill-through from Quality Analytics | 1. Right-click data point 2. Select drill-through 3. Verify target page inherits filters. | Mock Production Data (Sprint 4) | System successfully completes 'Auditor Drill-down' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-029 | RTM-029 | US-048 | Export QA Logs | BRD-03-01 | EP-03 | FT-020 | QA Export | N/A | Validate export feature for QA Export | 1. Apply filters 2. Click Export 3. Verify downloaded file contents match visuals. | Mock Production Data (Sprint 4) | System successfully completes 'Export QA Logs' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-030 | RTM-030 | US-050 | WFM Data Modeling | BRD-04-01 | EP-04 | FT-021 | WFM Landing | Scheduled Hours | Validate WFM Data Modeling functionality | 1. Navigate to WFM Landing 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'WFM Data Modeling' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | High | Mapped to RTM-01.
UAT-031 | RTM-031 | US-051 | Real-time Coverage | BRD-04-01 | EP-04 | FT-021 | WFM Coverage | Headcount Variance | Validate Real-time Coverage functionality | 1. Navigate to WFM Coverage 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Real-time Coverage' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-032 | RTM-032 | US-052 | Occupancy Gauge | BRD-04-01 | EP-04 | FT-022 | WFM Occupancy | Occupancy % | Validate Occupancy Gauge functionality | 1. Navigate to WFM Occupancy 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Occupancy Gauge' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-033 | RTM-033 | US-053 | Schedule Adherence | BRD-04-01 | EP-04 | FT-023 | WFM Adherence | Adherence % | Validate Schedule Adherence functionality | 1. Navigate to WFM Adherence 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Schedule Adherence' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-034 | RTM-034 | US-054 | Shrinkage Breakdown | BRD-04-01 | EP-04 | FT-024 | WFM Shrinkage | Shrinkage % | Validate Shrinkage Breakdown functionality | 1. Navigate to WFM Shrinkage 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Shrinkage Breakdown' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-035 | RTM-035 | US-055 | Shrinkage Alerts | BRD-04-01 | EP-04 | FT-024 | PBI Alerts | Unplanned Shrinkage | Validate Shrinkage Alerts functionality | 1. Navigate to PBI Alerts 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Shrinkage Alerts' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-036 | RTM-036 | US-056 | Absenteeism Trends | BRD-04-01 | EP-04 | FT-025 | WFM Trends | Absenteeism % | Validate Absenteeism Trends functionality | 1. Navigate to WFM Trends 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Absenteeism Trends' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-037 | RTM-037 | US-057 | Export WFM Data | BRD-04-01 | EP-04 | FT-026 | WFM Export | Actual Hours | Validate export feature for WFM Export | 1. Apply filters 2. Click Export 3. Verify downloaded file contents match visuals. | Mock Production Data (Sprint 4) | System successfully completes 'Export WFM Data' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | High | Mapped to RTM-01.
UAT-038 | RTM-038 | US-060 | Appeals Data Modeling | BRD-05-01 | EP-05 | FT-027 | Appeals Landing | Total Appeals | Validate Appeals Data Modeling functionality | 1. Navigate to Appeals Landing 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Appeals Data Modeling' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | High | Mapped to RTM-01.
UAT-039 | RTM-039 | US-061 | Appeals RLS | BRD-05-01 | EP-05 | FT-027 | Global Appeals Report | All | Validate Role-Level Security for Appeals Analytics | 1. Log in as restricted user 2. Navigate to report 3. Ensure unauthorized data is hidden. | Mock Production Data (Sprint 4) | System successfully completes 'Appeals RLS' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | High | Mapped to RTM-01.
UAT-040 | RTM-040 | US-062 | Appeals Intake | BRD-05-01 | EP-05 | FT-028 | Appeals Intake | Incoming Appeals | Validate Appeals Intake functionality | 1. Navigate to Appeals Intake 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Appeals Intake' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-041 | RTM-041 | US-063 | Appeals TAT | BRD-05-01 | EP-05 | FT-029 | Appeals Resolution | Appeals Avg TAT | Validate Appeals TAT functionality | 1. Navigate to Appeals Resolution 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Appeals TAT' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-042 | RTM-042 | US-064 | Disposition Pie | BRD-05-01 | EP-05 | FT-029 | Appeals Resolution | Disposition Volumes | Validate Disposition Pie functionality | 1. Navigate to Appeals Resolution 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Disposition Pie' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-043 | RTM-043 | US-065 | Aging Backlog | BRD-05-01 | EP-05 | FT-030 | Appeals Backlog | Open Appeals | Validate Aging Backlog functionality | 1. Navigate to Appeals Backlog 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Aging Backlog' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-044 | RTM-044 | US-066 | Overturn Rate | BRD-05-01 | EP-05 | FT-031 | Appeals Overturn | Overturn Rate % | Validate Overturn Rate functionality | 1. Navigate to Appeals Overturn 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Overturn Rate' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-045 | RTM-045 | US-067 | Export Appeals | BRD-05-01 | EP-05 | FT-032 | Appeals Export | N/A | Validate export feature for Appeals Export | 1. Apply filters 2. Click Export 3. Verify downloaded file contents match visuals. | Mock Production Data (Sprint 4) | System successfully completes 'Export Appeals' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-046 | RTM-046 | US-070 | Financial Data Integration | BRD-06-01 | EP-06 | FT-033 | Finance Landing | Gross Revenue | Validate Financial Data Integration functionality | 1. Navigate to Finance Landing 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Financial Data Integration' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | High | Mapped to RTM-01.
UAT-047 | RTM-047 | US-071 | Financial RLS | BRD-06-01 | EP-06 | FT-033 | Global Finance Report | All | Validate Role-Level Security for Financial Analytics | 1. Log in as restricted user 2. Navigate to report 3. Ensure unauthorized data is hidden. | Mock Production Data (Sprint 4) | System successfully completes 'Financial RLS' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | High | Mapped to RTM-01.
UAT-048 | RTM-048 | US-072 | Billable vs Non-Billable | BRD-06-01 | EP-06 | FT-034 | Finance Revenue | Billable Utilization | Validate Billable vs Non-Billable functionality | 1. Navigate to Finance Revenue 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Billable vs Non-Billable' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-049 | RTM-049 | US-073 | Gross Margin DAX | BRD-06-01 | EP-06 | FT-035 | Finance Margin | Gross Margin % | Validate Gross Margin DAX functionality | 1. Navigate to Finance Margin 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Gross Margin DAX' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-050 | RTM-050 | US-074 | Margin Trend | BRD-06-01 | EP-06 | FT-035 | Finance Margin | Gross Margin % | Validate Margin Trend functionality | 1. Navigate to Finance Margin 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Margin Trend' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-051 | RTM-051 | US-075 | Cost Per Ticket | BRD-06-01 | EP-06 | FT-036 | Finance Cost | Cost Per Ticket | Validate Cost Per Ticket functionality | 1. Navigate to Finance Cost 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Cost Per Ticket' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-052 | RTM-052 | US-076 | SLA Penalty | BRD-06-01 | EP-06 | FT-037 | Finance Penalties | Penalty Deductions | Validate SLA Penalty functionality | 1. Navigate to Finance Penalties 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'SLA Penalty' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-053 | RTM-053 | US-077 | Billing Reconciliation | BRD-06-01 | EP-06 | FT-038 | Finance Recon | Unbilled Variance | Validate Billing Reconciliation functionality | 1. Navigate to Finance Recon 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Billing Reconciliation' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-054 | RTM-054 | US-078 | Revenue Forecasting | BRD-06-01 | EP-06 | FT-039 | Finance Forecast | Projected Revenue | Validate Revenue Forecasting functionality | 1. Navigate to Finance Forecast 2. Verify visual renders correctly 3. Cross-check data with source. | Mock Production Data (Sprint 4) | System successfully completes 'Revenue Forecasting' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.
UAT-055 | RTM-055 | US-079 | Export Invoices | BRD-06-01 | EP-06 | FT-040 | Finance Export | N/A | Validate export feature for Finance Export | 1. Apply filters 2. Click Export 3. Verify downloaded file contents match visuals. | Mock Production Data (Sprint 4) | System successfully completes 'Export Invoices' per Acceptance Criteria. | To Be Executed | Business User |  | Not Executed | Medium | Mapped to RTM-01.

## 3_UAT_Defect_Log
Defect ID | Test Case ID | User Story | Defect Summary | Severity | Priority | Assigned To | Status | Resolution | Remarks
DEF-001 | UAT-003 | US-003 | [Illustrative Example] Date filter not defaulting to current month. | Medium | Medium | BI Dev Team | New |  | This is an illustrative entry. No actual defects logged.
DEF-002 | UAT-021 | US-021 | [Illustrative Example] RLS policy exposing cross-client data. | Critical | High | Security Admin | In Progress |  | This is an illustrative entry.
DEF-003 | UAT-079 | US-079 | [Illustrative Example] Export to Excel failing when rows > 100k. | High | Medium | BI Dev Team | Deferred |  | This is an illustrative entry.

## 4_Requirement_Coverage
Requirement ID | User Story | Dashboard | KPI | UAT Test Case | Coverage Status
BRD-01-01 | US-001 | Executive Landing | Total Volume, Global AHT | UAT-001 | Covered
BRD-01-01 | US-002 | Executive Header | Global AHT, Quality, Margin | UAT-002 | Covered
BRD-01-01 | US-003 | Executive Filters | All | UAT-003 | Covered
BRD-01-01 | US-005 | Executive Trends | Quality Score (MoM) | UAT-004 | Covered
BRD-01-01 | US-006 | Executive Summary | Volume, AHT, Quality | UAT-005 | Covered
BRD-01-01 | US-010 | Cross-Navigation | N/A | UAT-006 | Covered
BRD-01-01 | US-011 | Cross-Navigation | N/A | UAT-007 | Covered
BRD-01-01 | US-013 | Executive Export | All | UAT-008 | Covered
BRD-02-01 | US-020 | Ops Overview | Incoming, Handled Tickets | UAT-009 | Covered
BRD-02-01 | US-021 | Global Ops Report | All | UAT-010 | Covered
BRD-02-01 | US-022 | Ops Filters | All | UAT-011 | Covered
BRD-02-01 | US-023 | Ops SLA | SLA Attainment % | UAT-012 | Covered
BRD-02-01 | US-024 | PBI Alerts | Rolling SLA % | UAT-013 | Covered
BRD-02-01 | US-025 | Ops Productivity | AHT, Handled Count | UAT-014 | Covered
BRD-02-01 | US-026 | Ops Productivity | AHT Variance | UAT-015 | Covered
BRD-02-01 | US-027 | Ops Productivity | Utilization % | UAT-016 | Covered
BRD-02-01 | US-028 | Ops Backlog | Backlog Count | UAT-017 | Covered
BRD-02-01 | US-029 | Ops Trends | Incoming Volume | UAT-018 | Covered
BRD-02-01 | US-030 | Navigation | N/A | UAT-019 | Covered
BRD-02-01 | US-031 | Ops Export | All | UAT-020 | Covered
BRD-03-01 | US-040 | QA Landing | Total Audits | UAT-021 | Covered
BRD-03-01 | US-041 | Global QA Report | All | UAT-022 | Covered
BRD-03-01 | US-042 | QA Productivity | Audit Attainment % | UAT-023 | Covered
BRD-03-01 | US-043 | QA DAX | Fatal Error Rate % | UAT-024 | Covered
BRD-03-01 | US-044 | QA Breakdown | Error Count | UAT-025 | Covered
BRD-03-01 | US-045 | QA Coaching | Improvement % | UAT-026 | Covered
BRD-03-01 | US-046 | QA Trends | Quality Score | UAT-027 | Covered
BRD-03-01 | US-047 | QA Calibration | Average Score | UAT-028 | Covered
BRD-03-01 | US-048 | QA Export | N/A | UAT-029 | Covered
BRD-04-01 | US-050 | WFM Landing | Scheduled Hours | UAT-030 | Covered
BRD-04-01 | US-051 | WFM Coverage | Headcount Variance | UAT-031 | Covered
BRD-04-01 | US-052 | WFM Occupancy | Occupancy % | UAT-032 | Covered
BRD-04-01 | US-053 | WFM Adherence | Adherence % | UAT-033 | Covered
BRD-04-01 | US-054 | WFM Shrinkage | Shrinkage % | UAT-034 | Covered
BRD-04-01 | US-055 | PBI Alerts | Unplanned Shrinkage | UAT-035 | Covered
BRD-04-01 | US-056 | WFM Trends | Absenteeism % | UAT-036 | Covered
BRD-04-01 | US-057 | WFM Export | Actual Hours | UAT-037 | Covered
BRD-05-01 | US-060 | Appeals Landing | Total Appeals | UAT-038 | Covered
BRD-05-01 | US-061 | Global Appeals Report | All | UAT-039 | Covered
BRD-05-01 | US-062 | Appeals Intake | Incoming Appeals | UAT-040 | Covered
BRD-05-01 | US-063 | Appeals Resolution | Appeals Avg TAT | UAT-041 | Covered
BRD-05-01 | US-064 | Appeals Resolution | Disposition Volumes | UAT-042 | Covered
BRD-05-01 | US-065 | Appeals Backlog | Open Appeals | UAT-043 | Covered
BRD-05-01 | US-066 | Appeals Overturn | Overturn Rate % | UAT-044 | Covered
BRD-05-01 | US-067 | Appeals Export | N/A | UAT-045 | Covered
BRD-06-01 | US-070 | Finance Landing | Gross Revenue | UAT-046 | Covered
BRD-06-01 | US-071 | Global Finance Report | All | UAT-047 | Covered
BRD-06-01 | US-072 | Finance Revenue | Billable Utilization | UAT-048 | Covered
BRD-06-01 | US-073 | Finance Margin | Gross Margin % | UAT-049 | Covered
BRD-06-01 | US-074 | Finance Margin | Gross Margin % | UAT-050 | Covered
BRD-06-01 | US-075 | Finance Cost | Cost Per Ticket | UAT-051 | Covered
BRD-06-01 | US-076 | Finance Penalties | Penalty Deductions | UAT-052 | Covered
BRD-06-01 | US-077 | Finance Recon | Unbilled Variance | UAT-053 | Covered
BRD-06-01 | US-078 | Finance Forecast | Projected Revenue | UAT-054 | Covered
BRD-06-01 | US-079 | Finance Export | N/A | UAT-055 | Covered

## 5_UAT_Execution_Dashboard
UAT Execution Summary Dashboard
Test Cases by Epic
EP-02 | 12
EP-06 | 10
EP-03 | 9
EP-01 | 8
EP-04 | 8
EP-05 | 8
Test Cases by Status
Not Executed | 55
Test Cases by Severity
Medium | 45
High | 10

## 6_Business_Sign-off
Business Sign-off & Formal Acceptance
Business Readiness Checklist
Business Requirements Verified | [ ] Yes / [ ] No
Functional Requirements Verified | [ ] Yes / [ ] No
KPI Validation Completed | [ ] Yes / [ ] No
Dashboard Validation Completed | [ ] Yes / [ ] No
User Acceptance Completed (No Open Critical Defects) | [ ] Yes / [ ] No
End-User Training Completed | [ ] Yes / [ ] No
Documentation Reviewed & Accepted | [ ] Yes / [ ] No
Sign-off Table
Role | Name | Signature | Date
Product Owner
Business Sponsor
Project Manager
Business Analyst
QA Lead
Note: This section is to be completed ONLY when all UAT Exit Criteria have been successfully met.